# Change Request CR-007: Intercompany Auto-Settlement for ZVQA

Zava Horizon programme (ZAV-HZN) – Zava Logistics FZE and Frontier Consulting

# 1. Change request details

| CR number | ZAV-HZN CR-007 |
| --- | --- |
| Title | Intercompany Auto-Settlement for ZVQA |
| Programme / project code | Zava Horizon / ZAV-HZN |
| Requester (customer) | Hassan Ali, Group Financial Controller, Zava Logistics FZE |
| Prepared by (Frontier) | James Okafor, F&O Solution Architect / Finance lead, Frontier Consulting |
| Date raised | Tue 6 Oct 2026 |
| Workstream | Finance (lead: James Okafor) |
| Priority | High |
| Status | Submitted for SteerCo |
| Decision forum | Zava Horizon Steering Committee, Wed 28 Oct 2026, 10:00–11:30 |
| Version | 1.0 |

# 2. Description of the change

The signed-off design (4 Sep 2026) uses standard Dynamics 365 Finance intercompany accounting for all five legal entities, with intercompany balances for ZVQA (Qatar) settled manually by the ZVQA finance team at month end. This mirrors how ZVQA works today in Dynamics GP 2018, where recharges from ZVAE and ZVHQ are reconciled in spreadsheets.

This change request asks Frontier to configure automatic intercompany settlement for ZVQA. Intercompany customer and vendor invoices between ZVQA, ZVAE and ZVHQ would be settled automatically by a scheduled batch job, with netting of open balances by counterparty and currency (QAR and AED) and automatic posting of realised exchange differences.

The scope also includes a netting exception report for the Group Financial Controller, updates to the ZVQA month-end close checklist, and additional SIT and UAT test scripts for the intercompany scenarios.

# 3. Business justification

Since design sign-off, ZVQA intercompany volumes have grown with new freight forwarding contracts in Qatar. Manual settlement would take the ZVQA finance team several days each month and raises the risk of unreconciled intercompany balances at group consolidation.

Automating settlement shortens the ZVQA close and reduces the load on the ZVQA finance team. This matters because UAT (11–29 Jan 2027) already clashes with the ZVQA year-end close, so the same people would be needed for both.

# 4. Options considered

| Option | Description | Effort | Assessment |
| --- | --- | --- | --- |
| A. No change (manual settlement as designed) | ZVQA finance team settles intercompany balances manually each month in D365 Finance. | 0 days | No cost to the programme, but the manual effort and reconciliation risk continue after go-live. |
| B. Automatic settlement and netting for ZVQA (recommended) | Configure automatic settlement, a scheduled batch job, QAR/AED netting and an exception report. | 18 days | Removes the manual effort and fits the standard product with a light extension. It adds load to the Finance workstream in Sprint 5. |
| C. Defer to a post go-live release | Go live with manual settlement and deliver option B after hypercare (from Apr 2027). | 18 days plus regression testing | Protects build capacity now, but ZVQA runs its first close in D365 manually and the change needs a separate test cycle later. |

Frontier recommends option B, subject to the PMO assessment of the impact on the Build sprints and test windows.

# 5. Estimate

The estimate below is based on Frontier day rates and is charged as a change to the fixed fee. It covers design update, configuration, the batch job and exception report, testing support and documentation.

| Role | Resource | Day rate (AED) | Days | Cost (AED) |
| --- | --- | --- | --- | --- |
| Architect | James Okafor | 6,500 | 3 | 19,500 |
| Functional consultant | Finance functional consultant | 5,200 | 7 | 36,400 |
| Developer | Arjun Mehta | 4,800 | 5 | 24,000 |
| Project manager | Priya Nair | 6,000 | 2 | 12,000 |
| Data migration | Noura Al Hashimi | 4,800 | 1 | 4,800 |
| Total |  |  | 18 | 96,700 |

Total estimate: 18 days, AED 96,700 (excluding VAT). The estimate is valid for 30 days from the date raised.

Assumption: the ZVQA intercompany account mapping is confirmed by Zava before work starts. Out of scope: changes to the group consolidation process.

# 6. Dependencies

Intercompany chart of accounts mapping for ZVQA, ZVAE and ZVHQ signed off by Hassan Ali.

ZVQA opening intercompany balances included in the next mock data migration (Data Migration workstream, Noura Al Hashimi).

Finance workstream capacity in Build Sprint 5 (ends Fri 6 Nov 2026).

UAT resourcing plan for ZVQA (SteerCo action owned by Hassan Ali) covering the additional intercompany test scripts.

# 7. Risks

| Risk | Likelihood | Impact | Proposed mitigation |
| --- | --- | --- | --- |
| ZVQA key users unavailable for UAT because of the year-end close. | High | High | Agree the ZVQA UAT resourcing plan and schedule intercompany scripts early in the UAT window. |
| Rounding differences when netting QAR and AED balances. | Medium | Medium | Define tolerance accounts and test with real ZVQA balances in SIT. |
| Additional load on the Finance workstream during Sprint 5. | Medium | Medium | Re-plan the Sprint 5 backlog with James Okafor before approval. |

# 8. Impact on go-live and programme (for assessment)

This section is completed by the PMO after the change request is logged. It remains open until the PMO assessment is finished and is reviewed at the SteerCo before a decision is taken.

| Impact area | Assessment |
| --- | --- |
| Impact on timeline | TBC by PMO |
| Impact on go-live (Mon 1 Mar 2027) | TBC by PMO |
| Impact on SIT (30 Nov–18 Dec 2026) and UAT (11–29 Jan 2027) |  |
| Impact on budget and contingency | AED 96,700 requested against programme contingency (AED 0.6m). Remaining contingency: TBC by PMO. |
| Impact on other workstreams |  |
| PMO assessment completed by / date |  |

# 9. Approval

Approval below authorises Frontier Consulting to proceed on the basis of the estimate in section 5. Any drawdown from contingency is recorded in the programme change log by the PMO.

| Role | Name | Decision (Approve / Reject / Defer) | Signature | Date |
| --- | --- | --- | --- | --- |
| Executive Sponsor (Chair, SteerCo) | Nadia Farouk, CFO, Zava Logistics FZE |  |  |  |
| Customer IT Director | Ravi Kumar, IT Director, Zava Logistics FZE |  |  |  |
| Group Financial Controller | Hassan Ali, Zava Logistics FZE |  |  |  |
| Frontier Practice Lead | Lorette Roos, Practice Lead, Business Applications, Frontier Consulting |  |  |  |
| Frontier Project Manager | Priya Nair, Project Manager, Frontier Consulting |  |  |  |

Fictitious test data – Copilot for Frontier Consultancy scenario testing