## Read me
Frontier Project Actuals – Zava Industrial Distribution
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Item | Detail
Purpose | Closed-project actuals from a comparable Frontier Consulting implementation, used as historical evidence when estimating new D365 bids (e.g. Zava, ZAV-RFP-2026-014). Copilot uses it to sanity-check estimates and apply lessons learned.
Test-data notice | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious.
Customer | Zava Industrial Distribution LLC – distributor of industrial equipment, pumps, valves and electrical supplies; HQ Dubai, branches in Abu Dhabi and Dammam (fictitious).
Scope | D365 Sales, D365 Customer Service, D365 Finance; Power BI; 6 integrations; 8 data migration objects.
Timeline | Kick-off 6 Jan 2025 · Go-live 1 Dec 2025 · Hypercare to 31 Jan 2026 · Project closed 27 Feb 2026.
Frontier team | Practice Lead: Lorette Roos · Lead Solution Architect: Omar Khalil · Finance lead: James Okafor · PM: Priya Nair · CE Functional Lead: Lina Mansour · Technical Lead: Arjun Mehta · Data Migration Lead: Noura Al Hashimi
Headline variances | Data migration +38% · Integrations +27% · Reports +22% · Configuration, forms and workflows within ±10%.
Units | All effort in person-days. Variance % = (Actual − Estimated) ÷ Estimated.
Sheet map
Actuals | 45 work packages with item type, complexity, estimated and actual days, variance and comment; totals by formula.
Variance by Item Type | Roll-up by item type (SUMIF formulas) with lessons learned.
Fictitious test data – Copilot for Frontier Consultancy scenario testing

## Actuals
Zava Industrial Distribution – D365 implementation: estimate vs actual (closed project)
D365 Sales + Customer Service + Finance · Project closed 27 Feb 2026 · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Work package | Item type | Complexity | Estimated days | Actual days | Variance % | Comment
Sales – Account, contact & hierarchy model | Configuration | Medium | 6 | 6.5 | 8.333% | Minor rework after hierarchy workshop
Sales – Lead-to-opportunity business process flow | Workflow/Power Automate | Medium | 5 | 5.5 | 10% | Extra stage (Site Visit) added in design
Sales – Product catalogue & price lists | Configuration | Medium | 8 | 8.5 | 6.25% | Three currencies; contract prices added
Sales – Quote document template (Word) | Configuration | Simple | 3 | 3.5 | 16.67% | English only; Arabic layout descoped
Sales – Quote discount approval flow | Workflow/Power Automate | Medium | 5 | 4.5 | -10% | Reused standard approval pattern
Sales – Credit-hold check plug-in | Plug-in | Medium | 8 | 9.5 | 18.75% | Finance API response slower than expected; caching added
Sales – Opportunity & quote forms and views | Form/view | Medium | 6 | 6 | 0% | As estimated
Sales – Security roles & business units | Configuration | Medium | 4 | 4.5 | 12.5% | Extra role for branch managers
Customer Service – Case model & categories | Configuration | Medium | 5 | 5 | 0% | As estimated
Customer Service – Unified routing & queues | Configuration | Complex | 10 | 11.5 | 15% | Skills-based routing tuned during UAT
Customer Service – SLA & business-hours calendars | Configuration | Complex | 8 | 9 | 12.5% | Public-holiday calendars for 3 countries
Customer Service – Email-to-case & templates | Configuration | Simple | 4 | 4 | 0% | As estimated
Customer Service – Knowledge base (English/Arabic) | Configuration | Medium | 4 | 3.5 | -12.5% | Customer loaded articles themselves
Customer Service – Agent workspace forms & dashboards | Form/view | Medium | 6 | 6.5 | 8.333% | Additional supervisor dashboard
Customer Service – Warranty validation plug-in | Plug-in | Complex | 9 | 10 | 11.11% | Serial-number lookup edge cases
Finance – Chart of accounts & financial dimensions | Configuration | Complex | 10 | 10.5 | 5% | Late change to cost-centre structure
Finance – Legal entities & multi-currency | Configuration | Medium | 6 | 6 | 0% | As estimated
Finance – VAT set-up UAE / KSA / Oman | Configuration | Complex | 9 | 10 | 11.11% | KSA reverse-charge scenarios added
Finance – Accounts payable & three-way matching | Configuration | Medium | 7 | 7 | 0% | As estimated
Finance – Accounts receivable, collections & PDC | Configuration | Complex | 9 | 9.5 | 5.556% | PDC bounce process clarified in UAT
Finance – Fixed assets | Configuration | Medium | 5 | 5 | 0% | As estimated
Finance – Bank reconciliation (MT940) | Configuration | Medium | 6 | 7 | 16.67% | One bank's MT940 format non-standard
Finance – Intercompany & eliminations | X++ class | Complex | 10 | 11 | 10% | Extra settlement batch job
Finance – Journal & invoice approval workflows | Workflow/Power Automate | Medium | 5 | 5 | 0% | As estimated
Finance – Bank payment file formats (ER) | Extension | Medium | 6 | 6.5 | 8.333% | Bank format revision mid-project
Report – Management P&L by branch (financial reports) | Report | Complex | 12 | 15 | 25% | Row definitions rebuilt after CoA change
Report – AR ageing & collections (Power BI) | Report | Medium | 8 | 9.5 | 18.75% | Additional drill-through requested
Report – Sales pipeline dashboard (Power BI) | Report | Medium | 8 | 9 | 12.5% | Row-level security by branch
Report – Service SLA dashboard (Power BI) | Report | Medium | 8 | 10.5 | 31.25% | SLA KPI definitions changed twice
Report – Bilingual tax invoice (SSRS) | Report | Complex | 10 | 12.5 | 25% | Arabic font rendering issues in PDF
Report – Executive KPI dashboard (Power BI) | Report | Simple | 4 | 4.5 | 12.5% | Minor visual changes
Integration – Dual-write CE ↔ Finance (customers, products, orders) | Integration | Complex | 25 | 31 | 24% | Initial sync failures; custom maps for party model
Integration – Bank host-to-host payments | Integration | Complex | 20 | 26 | 30% | Bank certification cycle took 3 extra weeks
Integration – Telephony CTI screen-pop | Integration | Medium | 12 | 14 | 16.67% | Vendor connector version mismatch
Integration – Website lead-capture API | Integration | Simple | 6 | 7 | 16.67% | Additional spam filtering
Integration – Courier tracking API | Integration | Medium | 12 | 16.5 | 37.5% | Courier API rate limits; batching redesign
Integration – Legacy WMS stock feed | Integration | Complex | 25 | 32.5 | 30% | Legacy WMS undocumented; reverse-engineered file layout
Data migration – Customers & contacts | Data migration object | Complex | 10 | 15 | 50% | High duplicate rate in legacy CRM; extra cleansing cycles
Data migration – Vendors | Data migration object | Medium | 6 | 9 | 50% | Vendor master duplicates and missing bank details
Data migration – Products / released products | Data migration object | Medium | 6 | 8 | 33.33% | Unit-of-measure conversions incomplete
Data migration – Open sales orders | Data migration object | Medium | 6 | 8 | 33.33% | Two additional mock loads
Data migration – Open AR invoices | Data migration object | Medium | 6 | 8.5 | 41.67% | Reconciliation differences with legacy aged debt
Data migration – Open AP invoices | Data migration object | Simple | 3 | 4 | 33.33% | Extra mock load
Data migration – GL opening balances | Data migration object | Medium | 6 | 7.5 | 25% | Late audit adjustments
Data migration – Historical cases (24 months) | Data migration object | Simple | 7 | 9 | 28.57% | Attachment volumes larger than profiled
Total |  |  | 364 | 432.5 | 18.82% | 45 work packages

## Variance by Item Type
Variance by item type – where estimates ran over
Calculated from the Actuals sheet · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Item type | Work packages | Estimated days | Actual days | Variance (days) | Variance %
Configuration | 16 | 104 | 111 | 7 | 6.731%
Form/view | 2 | 12 | 12.5 | 0.5 | 4.167%
Workflow/Power Automate | 3 | 15 | 15 | 0 | 0%
Plug-in | 2 | 17 | 19.5 | 2.5 | 14.71%
X++ class | 1 | 10 | 11 | 1 | 10%
Extension | 1 | 6 | 6.5 | 0.5 | 8.333%
Report | 6 | 50 | 61 | 11 | 22%
Integration | 6 | 100 | 127 | 27 | 27%
Data migration object | 8 | 50 | 69 | 19 | 38%
Total | 45 | 364 | 432.5 | 68.5 | 18.82%
Check: matches Actuals total (should be 0) |  | 0 | 0
Lessons learned
Data migration ran 38% over: legacy master data (customers, vendors) had high duplicate rates; budget at least 3 mock loads and a cleansing owner on the customer side.
Integrations ran 27% over: third-party dependencies (bank certification, courier API limits, undocumented legacy WMS) – secure API specifications before fixing price.
Reports ran 22% over: KPI definitions and the chart of accounts changed late; freeze report definitions at design sign-off and treat bilingual (Arabic) layouts as Complex.
Configuration, forms and workflows landed within ±10% of estimate – the complexity matrix is reliable for these item types.