## Read me
ZAV-HZN Cutover Plan v0.3
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Purpose | Draft cutover runbook (v0.3) for the Zava Horizon go-live: D365 Finance + Supply Chain (F&O) and D365 Sales / Customer Service (CE). Cutover weekend Fri 26 Feb – Sun 28 Feb 2027, go-live Mon 1 Mar 2027. Use for testing runbook review, dependency checking, critical path, Go/No-Go preparation and owner briefings.
Programme | Zava Horizon (ZAV-HZN) – Zava LLC, delivered by Frontier Consulting
Data as of | Monday 19 Oct 2026 (Dubai, UTC+4)
As-of date (used in formulas) | 2026-10-19
Currency | AED
Prepared by | Priya Nair, Project Manager (Frontier Consulting) – scenario owner Lorette Roos
Sheet | Contents
Runbook | 112 tasks across Pre-cutover (T-14 to T-1), Freeze, Data migration, Technical, Business validation, three Go/No-Go gates, Go-live and Hypercare day 1. Planned end = planned start + duration.
Phase summary | Task counts, earliest start, latest finish and total hours by phase (formulas).
Version | v0.3 DRAFT – for review at design authority; not yet baselined. Times are Gulf Standard Time (UTC+4).
Go/No-Go gates | Gate 1 Fri 26 Feb (start data migration) ¦ Gate 2 Sat 27 Feb (start business validation) ¦ Gate 3 Sun 28 Feb 16:00 (final Go/No-Go)
Important | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious and must not be used for real decisions.

## Runbook
ZAV-HZN Cutover Plan v0.3 (DRAFT) ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Task ID | Phase | Task | Planned start | Planned end | Duration (h) | Predecessor IDs | Owner | Team | Status | Evidence required | Comments
CUT-001 | Pre-cutover (T-14 to T-1) | Cutover plan v1.0 baselined and circulated | 2027-02-12 09:00 | 2027-02-12 13:00 | 4 |  | Priya Nair | PMO | In planning | Signed cutover plan | T-14
CUT-002 | Pre-cutover (T-14 to T-1) | Confirm cutover roles, rota and contact list | 2027-02-12 13:00 | 2027-02-12 17:00 | 4 | CUT-001 | Priya Nair | PMO | In planning | Contact list in Teams channel
CUT-003 | Pre-cutover (T-14 to T-1) | Production environment deployed with final release package | 2027-02-12 10:00 | 2027-02-12 18:00 | 8 |  | Arjun Mehta | Frontier – Integration | In planning | LCS/PPAC deployment log
CUT-004 | Pre-cutover (T-14 to T-1) | CE production solutions imported (managed) | 2027-02-12 18:00 | 2027-02-12 22:00 | 4 | CUT-003 | Arjun Mehta | Frontier – CE | In planning | Solution import history
CUT-005 | Pre-cutover (T-14 to T-1) | Security roles and user access provisioned in F&O and CE | 2027-02-15 09:00 | 2027-02-16 01:00 | 16 | CUT-003 | Ravi Kumar | Zava IT | Not started | User access report
CUT-006 | Pre-cutover (T-14 to T-1) | Final mock cutover (Mock 3) results signed off | 2027-02-15 09:00 | 2027-02-15 17:00 | 8 |  | Noura Al Hashimi | Frontier – Data | Not started | Mock 3 reconciliation pack | Mock 3 ran 6–7 Feb
CUT-007 | Pre-cutover (T-14 to T-1) | Static master data loaded to production (COA, dimensions, posting profiles) | 2027-02-15 13:00 | 2027-02-16 01:00 | 12 | CUT-003, CUT-006 | Noura Al Hashimi | Frontier – Data | Not started | Load log and record counts
CUT-008 | Pre-cutover (T-14 to T-1) | Vendor master (de-duplicated) loaded to production | 2027-02-16 01:00 | 2027-02-16 09:00 | 8 | CUT-007 | Noura Al Hashimi | Frontier – Data | Not started | Dedup report and load log
CUT-009 | Pre-cutover (T-14 to T-1) | Customer master loaded to production | 2027-02-16 09:00 | 2027-02-16 17:00 | 8 | CUT-008 | Noura Al Hashimi | Frontier – Data | Not started | Load log
CUT-010 | Pre-cutover (T-14 to T-1) | Vendor and customer master sign-off by Group Financial Controller | 2027-02-16 17:00 | 2027-02-16 21:00 | 4 | CUT-009 | Hassan Ali | Zava Finance | Not started | Signed master data sign-off
CUT-011 | Pre-cutover (T-14 to T-1) | Fixed asset register loaded and reconciled | 2027-02-16 21:00 | 2027-02-17 05:00 | 8 | CUT-010 | James Okafor | Frontier – Finance | Not started | FA reconciliation
CUT-012 | Pre-cutover (T-14 to T-1) | Warehouse locations, zones and license plates set up | 2027-02-16 09:00 | 2027-02-16 21:00 | 12 | CUT-007 | Rahul Verma | Frontier – Supply Chain | Not started | Location count report
CUT-013 | Pre-cutover (T-14 to T-1) | Warehouse mobile devices configured and tested on production | 2027-02-17 09:00 | 2027-02-17 17:00 | 8 | CUT-012 | Grace Lee | Zava Warehouse | Not started | Device test checklist
CUT-014 | Pre-cutover (T-14 to T-1) | Trade agreements and freight rate cards loaded | 2027-02-16 09:00 | 2027-02-16 17:00 | 8 | CUT-007 | Lina Mansour | Frontier – CE | Not started | Rate card comparison
CUT-015 | Pre-cutover (T-14 to T-1) | CargoWise production connection tested (read-only) | 2027-02-17 09:00 | 2027-02-17 15:00 | 6 | CUT-003 | Arjun Mehta | Frontier – Integration | Not started | Connection test log
CUT-016 | Pre-cutover (T-14 to T-1) | ZATCA e-invoicing ISV production onboarding for ZVSA | 2027-02-17 15:00 | 2027-02-17 23:00 | 8 | CUT-015 | James Okafor | Frontier – Finance | Not started | ZATCA onboarding certificate (CSID)
CUT-017 | Pre-cutover (T-14 to T-1) | Bank integration production certificates installed (UAE, KSA, Oman) | 2027-02-17 23:00 | 2027-02-18 05:00 | 6 | CUT-016 | Ravi Kumar | Zava IT | Not started | Certificate install log
CUT-018 | Pre-cutover (T-14 to T-1) | Batch jobs created (disabled) and schedule documented | 2027-02-18 09:00 | 2027-02-18 15:00 | 6 | CUT-003 | Arjun Mehta | Frontier – Integration | Not started | Batch job list
CUT-019 | Pre-cutover (T-14 to T-1) | Printer and label configuration for warehouse documents | 2027-02-18 15:00 | 2027-02-18 19:00 | 4 | CUT-018 | Ravi Kumar | Zava IT | Not started | Test print evidence
CUT-020 | Pre-cutover (T-14 to T-1) | End-user training completion confirmed (>= 90%) | 2027-02-18 09:00 | 2027-02-18 13:00 | 4 |  | Tom Becker | Frontier – Change | Not started | Training completion report
CUT-021 | Pre-cutover (T-14 to T-1) | Go-live communications issued to staff and customers | 2027-02-18 13:00 | 2027-02-18 15:00 | 2 | CUT-020 | Elena Petrova | Zava HR & Change | Not started | Comms email and intranet post
CUT-022 | Pre-cutover (T-14 to T-1) | Legacy GP 2018 and Tally period-end close completed (Jan 2027) | 2027-02-19 09:00 | 2027-02-20 01:00 | 16 |  | Hassan Ali | Zava Finance | Not started | Close checklist
CUT-023 | Pre-cutover (T-14 to T-1) | Hypercare support model and ticket queues ready | 2027-02-22 09:00 | 2027-02-22 13:00 | 4 |  | Priya Nair | PMO | Not started | Hypercare runbook
CUT-024 | Pre-cutover (T-14 to T-1) | Cutover rehearsal walkthrough (table-top) | 2027-02-23 10:00 | 2027-02-23 13:00 | 3 | CUT-002 | Priya Nair | PMO | Not started | Attendance and actions
CUT-025 | Pre-cutover (T-14 to T-1) | Open items extract scripts validated against Mock 3 | 2027-02-23 14:00 | 2027-02-23 18:00 | 4 | CUT-006 | Noura Al Hashimi | Frontier – Data | Not started | Script sign-off
CUT-026 | Pre-cutover (T-14 to T-1) | Customer and vendor notification of new bank details/invoice format | 2027-02-23 18:00 | 2027-02-23 22:00 | 4 | CUT-025 | Samir Haddad | Zava Customer Service | Not started | Notification log
CUT-027 | Pre-cutover (T-14 to T-1) | Readiness checkpoint with sponsor (T-2) | 2027-02-24 11:00 | 2027-02-24 12:00 | 1 | CUT-024, CUT-025 | Nadia Farouk | Zava Sponsor | Not started | Readiness checklist | T-2
CUT-028 | Pre-cutover (T-14 to T-1) | Final backup of legacy systems scheduled | 2027-02-25 09:00 | 2027-02-25 11:00 | 2 |  | Ravi Kumar | Zava IT | Not started | Backup schedule
CUT-029 | Freeze | Freeze new sales quotes and orders in Salesforce / legacy | 2027-02-26 12:00 | 2027-02-26 13:00 | 1 | CUT-027 | Lina Mansour | Frontier – CE | Not started | Freeze confirmation email
CUT-030 | Freeze | Freeze AP invoice entry in GP 2018 and Tally | 2027-02-26 12:00 | 2027-02-26 13:00 | 1 | CUT-027 | Hassan Ali | Zava Finance | Not started | Freeze confirmation
CUT-031 | Freeze | Freeze AR invoicing and cash receipts in legacy | 2027-02-26 12:00 | 2027-02-26 13:00 | 1 | CUT-027 | Hassan Ali | Zava Finance | Not started | Freeze confirmation
CUT-032 | Freeze | Freeze warehouse transactions in legacy WMS (stock count start) | 2027-02-26 13:00 | 2027-02-26 14:00 | 1 | CUT-027 | Grace Lee | Zava Warehouse | Not started | Freeze confirmation
CUT-033 | Freeze | CargoWise outbound messages paused | 2027-02-26 13:00 | 2027-02-26 14:00 | 1 | CUT-027 | Arjun Mehta | Frontier – Integration | Not started | Queue screenshot
CUT-034 | Freeze | Physical stock count at Jebel Ali DC | 2027-02-26 14:00 | 2027-02-26 18:00 | 4 | CUT-033 | Grace Lee | Zava Warehouse | Not started | Signed count sheets
CUT-035 | Freeze | Legacy systems set to read-only | 2027-02-26 14:00 | 2027-02-26 15:00 | 1 | CUT-029, CUT-030, CUT-031 | Ravi Kumar | Zava IT | Not started | Access change record
CUT-036 | Freeze | Final legacy backups taken | 2027-02-26 15:00 | 2027-02-26 17:00 | 2 | CUT-035 | Ravi Kumar | Zava IT | Not started | Backup log
CUT-037 | Freeze | Closing trial balances extracted per entity (ZVAE, ZVSA, ZVOM, ZVQA, ZVHQ) | 2027-02-26 17:00 | 2027-02-26 19:00 | 2 | CUT-036 | James Okafor | Frontier – Finance | Not started | Trial balance extracts
CUT-038 | Freeze | Freeze confirmation to cutover lead | 2027-02-26 19:00 | 2027-02-26 19:30 | 0.5 | CUT-034, CUT-037 | Priya Nair | PMO | Not started | Teams post in cutover channel
CUT-039 | Go/No-Go gates | Gate 1 pre-read: freeze, backups and trial balances complete | 2027-02-26 19:30 | 2027-02-26 20:00 | 0.5 | CUT-038 | Priya Nair | PMO | Not started | Gate 1 checklist
CUT-040 | Go/No-Go gates | Gate 1 – Go/No-Go to start data migration | 2027-02-26 20:00 | 2027-02-26 20:30 | 0.5 | CUT-039 | Nadia Farouk | Zava Sponsor | Not started | Gate 1 decision recorded | Go/No-Go gate 1
CUT-041 | Data migration | Open AR items extracted from legacy | 2027-02-26 20:30 | 2027-02-26 22:00 | 1.5 | CUT-040 | Noura Al Hashimi | Frontier – Data | Not started | Extract log
CUT-042 | Data migration | Open AR items transformed and validated | 2027-02-26 22:00 | 2027-02-26 23:30 | 1.5 | CUT-041 | Noura Al Hashimi | Frontier – Data | Not started | Validation report
CUT-043 | Data migration | Open AR items loaded to D365 Finance | 2027-02-26 23:30 | 2027-02-27 01:30 | 2 | CUT-042 | Noura Al Hashimi | Frontier – Data | Not started | Load log
CUT-044 | Data migration | Open AP items extracted from legacy | 2027-02-26 20:30 | 2027-02-26 22:00 | 1.5 | CUT-040 | Noura Al Hashimi | Frontier – Data | Not started | Extract log
CUT-045 | Data migration | Open AP items transformed and validated | 2027-02-26 22:00 | 2027-02-26 23:30 | 1.5 | CUT-044 | Noura Al Hashimi | Frontier – Data | Not started | Validation report
CUT-046 | Data migration | Load open AP invoices to D365 Finance | 2027-02-26 23:30 | 2027-02-27 01:30 | 2 | CUT-045, CUT-048 | Noura Al Hashimi | Frontier – Data | Not started | Load log
CUT-047 | Data migration | Validate AP load counts and amounts | 2027-02-27 01:30 | 2027-02-27 02:30 | 1 | CUT-046 | Hassan Ali | Zava Finance | Not started | Count reconciliation
CUT-048 | Data migration | Reconcile AP sub-ledger to GL | 2027-02-27 02:30 | 2027-02-27 03:30 | 1 | CUT-047 | James Okafor | Frontier – Finance | Not started | AP reconciliation
CUT-049 | Data migration | Opening GL balances loaded per entity | 2027-02-27 01:30 | 2027-02-27 03:30 | 2 | CUT-043 | James Okafor | Frontier – Finance | Not started | Journal posting log
CUT-050 | Data migration | Trial balance reconciliation legacy vs D365 (all entities) | 2027-02-27 03:30 | 2027-02-27 05:30 | 2 | CUT-049, CUT-048 | Hassan Ali | Zava Finance | Not started | Signed TB reconciliation
CUT-051 | Data migration | Bank balances loaded and reconciled | 2027-02-27 05:30 | 2027-02-27 06:30 | 1 | CUT-050 | James Okafor | Frontier – Finance | Not started | Bank reconciliation
CUT-052 | Data migration | Fixed asset NBV reconciled to GL | 2027-02-27 05:30 | 2027-02-27 06:30 | 1 | CUT-050 | James Okafor | Frontier – Finance | Not started | FA reconciliation
CUT-053 | Data migration | On-hand inventory loaded from stock count | 2027-02-26 20:30 | 2027-02-26 23:30 | 3 | CUT-034, CUT-040 | Rahul Verma | Frontier – Supply Chain | Not started | Inventory journal log
CUT-054 | Data migration | Inventory value reconciled to GL | 2027-02-27 05:30 | 2027-02-27 07:00 | 1.5 | CUT-053, CUT-050 | Hassan Ali | Zava Finance | Not started | Inventory reconciliation
CUT-055 | Data migration | Open purchase orders loaded | 2027-02-26 23:30 | 2027-02-27 01:30 | 2 | CUT-053 | Rahul Verma | Frontier – Supply Chain | Not started | Load log
CUT-056 | Data migration | Open sales orders and shipments loaded | 2027-02-27 01:30 | 2027-02-27 03:30 | 2 | CUT-055 | Lina Mansour | Frontier – CE | Not started | Load log
CUT-057 | Data migration | CE accounts and contacts migrated from Salesforce | 2027-02-26 20:30 | 2027-02-27 00:30 | 4 | CUT-040 | Lina Mansour | Frontier – CE | Not started | Migration log
CUT-058 | Data migration | CE open opportunities and quotes migrated | 2027-02-27 00:30 | 2027-02-27 03:30 | 3 | CUT-057 | Lina Mansour | Frontier – CE | Not started | Migration log
CUT-059 | Data migration | CE open cases migrated with SLA status | 2027-02-27 03:30 | 2027-02-27 06:30 | 3 | CUT-058 | Lina Mansour | Frontier – CE | Not started | Migration log
CUT-060 | Data migration | Dual-write / customer sync F&O-CE initial sync | 2027-02-27 03:30 | 2027-02-27 05:30 | 2 | CUT-057, CUT-056 | Arjun Mehta | Frontier – Integration | Not started | Sync status
CUT-061 | Data migration | Data migration error log reviewed and resolved | 2027-02-27 07:00 | 2027-02-27 09:00 | 2 | CUT-051, CUT-052, CUT-054, CUT-060 | Noura Al Hashimi | Frontier – Data | Not started | Error log
CUT-062 | Data migration | Data migration completion report issued | 2027-02-27 09:00 | 2027-02-27 10:00 | 1 | CUT-061 | Noura Al Hashimi | Frontier – Data | Not started | Completion report
CUT-063 | Technical | Batch jobs enabled (posting, settlement, revaluation) | 2027-02-27 10:00 | 2027-02-27 11:00 | 1 | CUT-062 | Arjun Mehta | Frontier – Integration | Not started | Batch job status
CUT-064 | Technical | CargoWise integration switched to production endpoints | 2027-02-27 11:00 | 2027-02-27 12:30 | 1.5 | CUT-063 | Arjun Mehta | Frontier – Integration | Not started | Endpoint config record
CUT-065 | Technical | CargoWise test shipment message round-trip | 2027-02-27 12:30 | 2027-02-27 13:30 | 1 | CUT-064 | Arjun Mehta | Frontier – Integration | Not started | Message trace
CUT-066 | Technical | Bank integration enabled and test payment file generated | 2027-02-27 11:00 | 2027-02-27 12:30 | 1.5 | CUT-063 | James Okafor | Frontier – Finance | Not started | Test payment file
CUT-067 | Technical | ZATCA e-invoicing for ZVSA – test invoice cleared | 2027-02-27 10:30 | 2027-02-27 11:30 | 1 | CUT-066 | James Okafor | Frontier – Finance | Not started | ZATCA clearance response | Can start in parallel with bank test
CUT-068 | Technical | Email-to-case and queues enabled in CE | 2027-02-27 11:00 | 2027-02-27 12:00 | 1 | CUT-063 | Lina Mansour | Frontier – CE | Not started | Mailbox test
CUT-069 | Technical | Power BI datasets refreshed against production | 2027-02-27 12:00 | 2027-02-27 13:30 | 1.5 | CUT-068 | James Okafor | Frontier – Finance | Not started | Refresh history
CUT-070 | Technical | Integration monitoring alerts enabled | 2027-02-27 13:30 | 2027-02-27 14:30 | 1 | CUT-065 | Arjun Mehta | Frontier – Integration | Not started | Alert test
CUT-071 | Technical | User access smoke test (sample of 20 users) | 2027-02-27 11:00 | 2027-02-27 13:00 | 2 | CUT-063 | Ravi Kumar | Zava IT | Not started | Access test log
CUT-072 | Technical | Warehouse mobile app connected to production | 2027-02-27 13:00 | 2027-02-27 14:00 | 1 | CUT-071 | Grace Lee | Zava Warehouse | Not started | Device login test
CUT-073 | Technical | Printing and label output tested | 2027-02-27 14:00 | 2027-02-27 15:00 | 1 | CUT-072 | Ravi Kumar | Zava IT | Not started | Test labels
CUT-074 | Technical | Technical readiness sign-off | 2027-02-27 15:00 | 2027-02-27 15:30 | 0.5 | CUT-064, CUT-065, CUT-066, CUT-067, CUT-068, CUT-069, CUT-070, CUT-071, CUT-072, CUT-073 | Omar Khalil | Frontier – Architecture | Not started | Technical sign-off
CUT-075 | Go/No-Go gates | Gate 2 pre-read: data reconciliations and technical readiness | 2027-02-27 15:30 | 2027-02-27 16:30 | 1 | CUT-074 | Priya Nair | PMO | Not started | Gate 2 checklist
CUT-076 | Go/No-Go gates | Gate 2 – Go/No-Go to start business validation | 2027-02-27 16:30 | 2027-02-27 17:00 | 0.5 | CUT-075, CUT-050 | Nadia Farouk | Zava Sponsor | Not started | Gate 2 decision recorded | Go/No-Go gate 2
CUT-077 | Business validation | Finance validation – trial balances per entity | 2027-02-27 17:00 | 2027-02-27 20:00 | 3 | CUT-076 | Hassan Ali | Zava Finance | Not started | Signed TB per entity
CUT-078 | Business validation | Finance validation – open AR and AP ageing | 2027-02-27 17:00 | 2027-02-27 20:00 | 3 | CUT-076 | Hassan Ali | Zava Finance | Not started | Ageing reports
CUT-079 | Business validation | Finance validation – intercompany balances net to zero | 2027-02-27 20:00 | 2027-02-27 22:00 | 2 | CUT-077 | James Okafor | Frontier – Finance | Not started | Intercompany report
CUT-080 | Business validation | ZVSA e-invoice issued and cleared by ZATCA | 2027-02-27 22:00 | 2027-02-27 23:00 | 1 | CUT-067, CUT-131 | James Okafor | Frontier – Finance | Not started | Clearance evidence
CUT-081 | Business validation | Test AP payment run (no release to bank) | 2027-02-27 20:00 | 2027-02-27 22:00 | 2 | CUT-078 | Hassan Ali | Zava Finance | Not started | Payment proposal
CUT-082 | Business validation | Warehouse validation – receive, putaway and pick test | 2027-02-27 17:00 | 2027-02-27 21:00 | 4 | CUT-076 | Grace Lee | Zava Warehouse | Not started | Test transaction list
CUT-083 | Business validation | Warehouse validation – stock on hand spot checks (50 SKUs) | 2027-02-27 21:00 | 2027-02-27 23:00 | 2 | CUT-082 | Grace Lee | Zava Warehouse | Not started | Spot check sheet
CUT-084 | Business validation | Freight quote created with trade agreement pricing | 2027-02-27 17:00 | 2027-02-27 18:30 | 1.5 | CUT-076 | Lina Mansour | Frontier – CE | Not started | Quote PDF
CUT-085 | Business validation | Sales validation – open opportunities and quotes | 2027-02-27 18:30 | 2027-02-27 20:30 | 2 | CUT-084 | Lina Mansour | Frontier – CE | Not started | Sample check sheet | Zava sales validator to be confirmed
CUT-086 | Business validation | Customer Service validation – cases, queues and SLA timers | 2027-02-27 17:00 | 2027-02-27 20:00 | 3 | CUT-076 | Samir Haddad | Zava Customer Service | Not started | Case test log
CUT-087 | Business validation | CargoWise shipment to invoice end-to-end test | 2027-02-27 17:00 | 2027-02-27 20:00 | 3 | CUT-076 | Arjun Mehta | Frontier – Integration | Not started | End-to-end trace
CUT-088 | Business validation | Power BI finance reports reviewed by Group Financial Controller | 2027-02-27 20:00 | 2027-02-27 21:00 | 1 | CUT-077 | Hassan Ali | Zava Finance | Not started | Report screenshots
CUT-089 | Business validation | Copilot in D365 and M365 features verified for pilot users | 2027-02-27 17:00 | 2027-02-27 18:00 | 1 | CUT-076 | Tom Becker | Frontier – Change | Not started | Feature checklist
CUT-090 | Business validation | Defect triage – business validation findings | 2027-02-27 23:00 | 2027-02-28 01:00 | 2 | CUT-079, CUT-080, CUT-081, CUT-083, CUT-086, CUT-087, CUT-088 | Priya Nair | PMO | Not started | Defect log
CUT-091 | Business validation | Business validation sign-off per workstream | 2027-02-28 01:00 | 2027-02-28 03:00 | 2 | CUT-090 | Priya Nair | PMO | Not started | Signed validation forms
CUT-092 | Go/No-Go gates | Gate 3 pre-read: validation sign-offs, open defects, rollback readiness | 2027-02-28 03:00 | 2027-02-28 04:00 | 1 | CUT-091 | Priya Nair | PMO | Not started | Gate 3 checklist
CUT-093 | Go/No-Go gates | Gate 3 – Final Go/No-Go decision | 2027-02-28 16:00 | 2027-02-28 17:00 | 1 | CUT-092 | Nadia Farouk | Zava Sponsor | Not started | Go-live decision minutes | Final Go/No-Go; rollback deadline Sun 22:00
CUT-094 | Go/No-Go gates | Communicate Go/No-Go outcome to all stakeholders | 2027-02-28 17:00 | 2027-02-28 17:30 | 0.5 | CUT-093 | Elena Petrova | Zava HR & Change | Not started | Comms email
CUT-095 | Go-live | Open periods in D365 Finance for March 2027 (all entities) | 2027-02-28 17:30 | 2027-02-28 18:00 | 0.5 | CUT-094 | James Okafor | Frontier – Finance | Not started | Period status
CUT-096 | Go-live | Release legacy systems to archive mode | 2027-02-28 17:30 | 2027-02-28 18:30 | 1 | CUT-094 | Ravi Kumar | Zava IT | Not started | Change record
CUT-097 | Go-live | Enable all users and remove cutover restrictions | 2027-02-28 18:00 | 2027-02-28 19:00 | 1 | CUT-095 | Ravi Kumar | Zava IT | Not started | Access change record
CUT-098 | Go-live | CargoWise outbound messages resumed | 2027-02-28 18:00 | 2027-02-28 18:30 | 0.5 | CUT-095 | Arjun Mehta | Frontier – Integration | Not started | Queue status
CUT-099 | Go-live | Batch job schedule switched to production timings | 2027-02-28 18:30 | 2027-02-28 19:00 | 0.5 | CUT-098 | Arjun Mehta | Frontier – Integration | Not started | Batch schedule
CUT-100 | Go-live | Copilot licences enabled for all 600 users | 2027-02-28 19:00 | 2027-02-28 20:00 | 1 | CUT-097 | Tom Becker | Frontier – Change | Not started | Licence report
CUT-101 | Go-live | Go-live announcement to staff and customers | 2027-03-01 07:00 | 2027-03-01 07:30 | 0.5 | CUT-097 | Elena Petrova | Zava HR & Change | Not started | Announcement post
CUT-102 | Go-live | Go-live – Mon 1 Mar 2027 business open | 2027-03-01 08:00 | 2027-03-01 08:30 | 0.5 | CUT-101 | Nadia Farouk | Zava Sponsor | Not started | Go-live confirmation
CUT-103 | Hypercare day 1 | Hypercare war room opened (Jebel Ali HQ and Teams) | 2027-03-01 07:00 | 2027-03-01 19:00 | 12 | CUT-095 | Priya Nair | PMO | Not started | War room log
CUT-104 | Hypercare day 1 | First sales orders and shipments processed | 2027-03-01 08:30 | 2027-03-01 11:30 | 3 | CUT-102 | Lina Mansour | Frontier – CE | Not started | Transaction list
CUT-105 | Hypercare day 1 | First warehouse waves released and picked | 2027-03-01 08:30 | 2027-03-01 11:30 | 3 | CUT-102 | Grace Lee | Zava Warehouse | Not started | Wave report
CUT-106 | Hypercare day 1 | First AR invoices posted and e-invoices cleared (ZVSA) | 2027-03-01 08:30 | 2027-03-01 11:30 | 3 | CUT-102 | James Okafor | Frontier – Finance | Not started | Invoice list
CUT-107 | Hypercare day 1 | CargoWise message monitoring – first 4 hours | 2027-03-01 08:30 | 2027-03-01 12:30 | 4 | CUT-102 | Arjun Mehta | Frontier – Integration | Not started | Monitoring dashboard
CUT-108 | Hypercare day 1 | Customer Service cases handled in D365 – first shift review | 2027-03-01 08:30 | 2027-03-01 12:30 | 4 | CUT-102 | Samir Haddad | Zava Customer Service | Not started | Case volume report
CUT-109 | Hypercare day 1 | Copilot adoption support desk open for pilot users | 2027-03-01 08:30 | 2027-03-01 16:30 | 8 | CUT-102 | Tom Becker | Frontier – Change | Not started | Support desk log
CUT-110 | Hypercare day 1 | Hypercare day 1 incident triage (P1/P2) | 2027-03-01 13:00 | 2027-03-01 15:00 | 2 | CUT-103 | Priya Nair | PMO | Not started | Incident log
CUT-111 | Hypercare day 1 | Day 1 end-of-day status report to sponsor | 2027-03-01 18:00 | 2027-03-01 19:00 | 1 | CUT-110 | Priya Nair | PMO | Not started | Status report
CUT-112 | Hypercare day 1 | Day 1 lessons learned and day 2 plan | 2027-03-01 19:00 | 2027-03-01 20:00 | 1 | CUT-111 | Priya Nair | PMO | Not started | Day 2 plan
Formulas:
Planned end = [Planned start]+[Duration (h)]/24

## Phase summary
ZAV-HZN cutover phase summary ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Phase | Tasks | Earliest start | Latest finish | Total task hours | Elapsed hours
Pre-cutover (T-14 to T-1) | 28 | 2027-02-12 09:00 | 2027-02-25 11:00 | 182 | 314
Freeze | 10 | 2027-02-26 12:00 | 2027-02-26 19:30 | 14.5 | 7.5
Data migration | 22 | 2027-02-26 20:30 | 2027-02-27 10:00 | 41.5 | 13.5
Technical | 12 | 2027-02-27 10:00 | 2027-02-27 15:30 | 14 | 5.5
Business validation | 15 | 2027-02-27 17:00 | 2027-02-28 03:00 | 32.5 | 10
Go/No-Go gates | 7 | 2027-02-26 19:30 | 2027-02-28 17:30 | 5 | 46
Go-live | 8 | 2027-02-28 17:30 | 2027-03-01 08:30 | 5.5 | 15
Hypercare day 1 | 10 | 2027-03-01 07:00 | 2027-03-01 20:00 | 41 | 13
Total | 112 | 2027-02-12 09:00 | 2027-03-01 20:00 | 336 | 419
Formulas:
Earliest start = MINIFS('Runbook'!$D3:D114,'Runbook'!$B3:B114,[Phase])
Earliest start = MIN(C3:[Earliest start, row above])
Latest finish = MAXIFS('Runbook'!$E3:E114,'Runbook'!$B3:B114,[Phase])
Latest finish = MAX(D3:[Latest finish, row above])