## Read me
ZAV-HZN Action Tracker
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Purpose | Meeting action log for the Zava Horizon programme, captured from daily stand-ups (09:15), design authority (Tue 14:00), PMO status (Thu 11:00) and monthly SteerCo. Use for testing overdue-action chasing, owner follow-ups, meeting preparation and status summaries.
Programme | Zava Horizon (ZAV-HZN) – Zava LLC, delivered by Frontier Consulting
Data as of | Monday 19 Oct 2026 (Dubai, UTC+4)
As-of date (used in formulas) | 2026-10-19
Currency | AED
Prepared by | Priya Nair, Project Manager (Frontier Consulting) – scenario owner Lorette Roos
Sheet | Contents
Actions | 40 actions with meeting, owner, due date, status and notes. 'Days overdue' and 'Overdue?' are calculated against the as-of date above.
Summary | Open, closed and overdue counts by meeting and by owner (formulas).
Overdue rule | Overdue = status not Closed and due date before the as-of date (19 Oct 2026).
Next SteerCo | Wed 28 Oct 2026 10:00–11:30 (previous: 30 Sep 2026)
Important | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious and must not be used for real decisions.

## Actions
ZAV-HZN Action Tracker ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Action ID | Meeting | Meeting date | Action | Owner | Due date | Status | Closed date | Notes | Days overdue | Overdue?
ACT-001 | SteerCo | 2026-08-26 | Confirm approach for ZATCA e-invoicing for ZVSA (ISV vs native) | James Okafor | 2026-09-16 | Closed | 2026-09-15 | Options paper issued; ISV route recommended. Decision on which ISV still open (see RAID I-002). |  | No
ACT-002 | SteerCo | 2026-08-26 | Nominate Zava SME for each workstream for Build | Elena Petrova | 2026-09-04 | Closed | 2026-09-03 | Names confirmed in PMO status 3 Sep. |  | No
ACT-003 | SteerCo | 2026-08-26 | Approve design sign-off plan for 4 Sep | Nadia Farouk | 2026-09-04 | Closed | 2026-09-04 | Design signed off 4 Sep 2026. |  | No
ACT-004 | SteerCo | 2026-09-30 | Escalate CargoWise API specification delay to vendor executive sponsor | Ravi Kumar | 2026-10-07 | In progress |  | Letter drafted; vendor call held 9 Oct but no committed date yet. | 12 | Yes
ACT-005 | SteerCo | 2026-09-30 | Decide ZATCA ISV for ZVSA | Nadia Farouk | 2026-10-14 | Open |  | Two ISVs shortlisted; awaiting commercial comparison from Hassan Ali. | 5 | Yes
ACT-006 | SteerCo | 2026-09-30 | Bring options for UAT clash with ZVQA year-end close | Priya Nair | 2026-10-21 | In progress |  | Two options drafted: split UAT or move ZVQA scripts into SIT week 3. |  | No
ACT-007 | SteerCo | 2026-09-30 | Present CR-007, CR-008 and CR-009 with impact and cost | Priya Nair | 2026-10-21 | In progress |  | CR-007 18 days; CR-008 45 days; CR-009 saves 12 days (pricing risk). |  | No
ACT-008 | SteerCo | 2026-09-30 | Approve contingency drawdown CD-01 for CargoWise rework (AED 120,000) | Nadia Farouk | 2026-09-30 | Closed | 2026-09-30 | Approved in meeting. |  | No
ACT-009 | PMO status | 2026-09-17 | Share revised spend forecast after August actuals | Priya Nair | 2026-09-24 | Closed | 2026-09-24 | Spend running 7% ahead of plan. |  | No
ACT-010 | PMO status | 2026-09-24 | Provide warehouse handheld device decision (Zebra vs Honeywell) | Grace Lee | 2026-10-08 | Open |  | Comparison sent 18 Sep; chased twice. | 11 | Yes
ACT-011 | PMO status | 2026-09-24 | Provision Azure integration environment (Logic Apps, Service Bus, Key Vault) in Zava tenant | Ravi Kumar | 2026-10-01 | In progress |  | Service Bus done; Logic Apps pending firewall rules. | 18 | Yes
ACT-012 | PMO status | 2026-10-01 | Confirm Copilot licence assignment report for all 600 users | Ravi Kumar | 2026-10-08 | Open |  | Needed before training wave 2. | 11 | Yes
ACT-013 | PMO status | 2026-10-01 | Circulate vendor de-duplication rules to Hassan Ali | Noura Al Hashimi | 2026-10-06 | Closed | 2026-10-05 | Rules covering 14% duplicates sent. |  | No
ACT-014 | PMO status | 2026-10-08 | Confirm golden vendor records for ZVAE and ZVOM | Hassan Ali | 2026-10-15 | Open |  | Hassan Ali on month-end close; delegate requested. | 4 | Yes
ACT-015 | PMO status | 2026-10-08 | Update RAID log owners and last-updated dates before SteerCo | Priya Nair | 2026-10-22 | Open |  | Several items not updated for 3+ weeks. |  | No
ACT-016 | PMO status | 2026-10-15 | Prepare SteerCo pack for 28 Oct | Priya Nair | 2026-10-26 | In progress |  | Draft due to Nadia Farouk 26 Oct. |  | No
ACT-017 | PMO status | 2026-10-15 | Book ZVQA finance team time for chart of accounts mapping workshop | Hassan Ali | 2026-10-16 | Open |  | Mapping 60% complete. | 3 | Yes
ACT-018 | PMO status | 2026-10-15 | Send remediation list for 37 overshared SharePoint sites to site owners | Tom Becker | 2026-10-20 | In progress |  | HR-Payroll and Finance-Board prioritised. |  | No
ACT-019 | Design authority | 2026-09-08 | Agree intercompany posting design across ZVAE, ZVSA, ZVOM, ZVQA and ZVHQ | James Okafor | 2026-09-22 | Closed | 2026-09-22 | Design approved in DA. |  | No
ACT-020 | Design authority | 2026-09-15 | Confirm CargoWise integration pattern (API vs file) as fallback | Arjun Mehta | 2026-09-29 | Closed | 2026-09-29 | API primary, file-based fallback agreed. |  | No
ACT-021 | Design authority | 2026-09-22 | Decide whether standard trade agreements replace rate-card engine (CR-009 input) | Rahul Verma | 2026-10-06 | Open |  | Waiting for quote comparison (200 historical quotes). | 13 | Yes
ACT-022 | Design authority | 2026-09-29 | Document case routing rules for Arabic and English queues | Lina Mansour | 2026-10-06 | Closed | 2026-10-06 | Reviewed with Samir Haddad. |  | No
ACT-023 | Design authority | 2026-10-06 | Confirm bank file formats for KSA and Oman house banks | James Okafor | 2026-10-13 | Open |  | UAE formats received; KSA and Oman outstanding. | 6 | Yes
ACT-024 | Design authority | 2026-10-06 | Review customer portal options for CR-008 (Power Pages vs custom) | Omar Khalil | 2026-10-20 | In progress |  | Power Pages preferred; estimate 45 days. |  | No
ACT-025 | Design authority | 2026-10-13 | Agree error handling standard for integrations | Arjun Mehta | 2026-10-27 | Open |  | Draft standard shared. |  | No
ACT-026 | Design authority | 2026-10-13 | Validate trade agreement pricing for 200 historical quotes | Lina Mansour | 2026-10-23 | In progress |  | 120 of 200 quotes compared; 6% variance on surcharges. |  | No
ACT-027 | Design authority | 2026-10-13 | Confirm sensitivity label taxonomy for Copilot rollout | Tom Becker | 2026-10-27 | Open |  | Elena Petrova to confirm HR labels. |  | No
ACT-028 | Daily stand-up | 2026-10-05 | Chase CargoWise vendor for draft API spec v0.9 | Arjun Mehta | 2026-10-07 | Closed | 2026-10-07 | Draft v0.9 received; final still pending. |  | No
ACT-029 | Daily stand-up | 2026-10-07 | Raise ticket for UAT environment storage capacity | Arjun Mehta | 2026-10-08 | Closed | 2026-10-08 | Resolved. |  | No
ACT-030 | Daily stand-up | 2026-10-08 | Pair with WMS developer on wave picking defects | Rahul Verma | 2026-10-09 | Closed | 2026-10-09 |  |  | No
ACT-031 | Daily stand-up | 2026-10-09 | Send Sprint 3 demo recording to Zava SMEs | Priya Nair | 2026-10-12 | Closed | 2026-10-12 |  |  | No
ACT-032 | Daily stand-up | 2026-10-12 | Re-plan Sprint 4 integration stories around CargoWise blockers | Arjun Mehta | 2026-10-14 | Closed | 2026-10-14 | 6 items moved to Blocked. |  | No
ACT-033 | Daily stand-up | 2026-10-13 | Fix SLA timer weekend pause bug | Lina Mansour | 2026-10-15 | Open |  | Still Active in Sprint 4. | 4 | Yes
ACT-034 | Daily stand-up | 2026-10-13 | Load customer master trial load 1 to Tier 2 | Noura Al Hashimi | 2026-10-14 | Closed | 2026-10-14 | 98.2% records loaded. |  | No
ACT-035 | Daily stand-up | 2026-10-14 | Confirm Arabic character fix for vendor names | Noura Al Hashimi | 2026-10-15 | Closed | 2026-10-15 |  |  | No
ACT-036 | Daily stand-up | 2026-10-15 | Share KSA bank payment file sample | James Okafor | 2026-10-16 | Open |  | Waiting on bank. | 3 | Yes
ACT-037 | Daily stand-up | 2026-10-15 | Update Power BI trial balance dataset for ZVQA | James Okafor | 2026-10-21 | In progress |  |  |  | No
ACT-038 | Daily stand-up | 2026-10-16 | Build CargoWise mock service from draft spec v0.9 | Arjun Mehta | 2026-10-22 | In progress |  | Blocked items can be partly unblocked with mock. |  | No
ACT-039 | Daily stand-up | 2026-10-16 | Prepare Copilot champions list by department | Tom Becker | 2026-10-23 | Open |  |  |  | No
ACT-040 | Daily stand-up | 2026-10-19 | Confirm Sprint 4 demo agenda for Fri 23 Oct | Priya Nair | 2026-10-22 | Open |  |  |  | No

## Summary
ZAV-HZN action summary ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Meeting | Total | Open / in progress | Closed | Overdue
Daily stand-up | 13 | 6 | 7 | 2
Design authority | 9 | 6 | 3 | 2
PMO status | 10 | 8 | 2 | 5
SteerCo | 8 | 4 | 4 | 2
Total | 40 | 24 | 16 | 11
Owner | Total | Open / in progress | Closed | Overdue
Arjun Mehta | 6 | 2 | 4 | 0
Elena Petrova | 1 | 0 | 1 | 0
Grace Lee | 1 | 1 | 0 | 1
Hassan Ali | 2 | 2 | 0 | 2
James Okafor | 5 | 3 | 2 | 2
Lina Mansour | 3 | 2 | 1 | 1
Nadia Farouk | 3 | 1 | 2 | 1
Noura Al Hashimi | 3 | 0 | 3 | 0
Omar Khalil | 1 | 1 | 0 | 0
Priya Nair | 7 | 5 | 2 | 0
Rahul Verma | 2 | 1 | 1 | 1
Ravi Kumar | 3 | 3 | 0 | 3
Tom Becker | 3 | 3 | 0 | 0