# Zava Horizon Steering Committee – Minutes

Programme ZAV-HZN – meeting of Wednesday 30 September 2026

| Date and time | Wed 30 Sep 2026, 10:00–11:30 (Dubai, UTC+4) |
| --- | --- |
| Location | Zava Logistics FZE, Jebel Ali Free Zone, Boardroom 2, and Microsoft Teams |
| Chair | Nadia Farouk, CFO and Executive Sponsor |
| Minutes | Priya Nair, Project Manager, Frontier Consulting |
| Status of minutes | Approved by the Chair on Fri 2 Oct 2026; action log updated by PMO on Fri 16 Oct 2026 |
| Next meeting | Wed 28 Oct 2026, 10:00–11:30 |

# 1. Attendees

| Name | Organisation | Role | Attendance |
| --- | --- | --- | --- |
| Nadia Farouk | Zava Logistics FZE | CFO, Executive Sponsor (Chair) | Present |
| Ravi Kumar | Zava Logistics FZE | IT Director | Present |
| Hassan Ali | Zava Logistics FZE | Group Financial Controller | Present |
| Grace Lee | Zava Logistics FZE | Head of Warehouse Operations | Present |
| Elena Petrova | Zava Logistics FZE | HR & Change Manager | Present (Teams) |
| Samir Haddad | Zava Logistics FZE | Customer Service Manager | Apologies |
| Lorette Roos | Frontier Consulting | Practice Lead, Business Applications | Present |
| Priya Nair | Frontier Consulting | Project Manager (minutes) | Present |
| James Okafor | Frontier Consulting | F&O Solution Architect / Finance lead | Present |
| Rahul Verma | Frontier Consulting | Supply Chain / Warehousing lead | Present (item 3) |
| Tom Becker | Frontier Consulting | Change & Adoption Lead (M365 Copilot) | Present (item 5) |

# 2. Previous minutes and actions

The minutes of the SteerCo held on Wed 26 Aug 2026 were approved without changes. All actions from that meeting were closed, including formal sign-off of the Design phase, which Nadia Farouk confirmed on Fri 4 Sep 2026.

# 3. Programme status

Priya Nair presented the status report. Overall programme status is AMBER. Build Sprint 2 closed on Fri 25 Sep 2026 and Sprint 3 is in progress (ends Fri 9 Oct 2026). The go-live date of Mon 1 Mar 2027 remains achievable, but the CargoWise integration delay is now on the critical path for SIT, which starts on Mon 30 Nov 2026.

| Workstream | Lead | RAG | Summary |
| --- | --- | --- | --- |
| Finance | James Okafor | GREEN | Sprint 2 scope delivered. ZATCA e-invoicing for ZVSA is tracked as a separate programme issue. |
| Supply Chain / Warehousing | Rahul Verma | AMBER | Mobile device decision for warehouse scanning is outstanding and blocks mobile app configuration and testing. |
| Sales & Service (CE) | Lina Mansour | GREEN | Sales and case management configuration on track. |
| Data Migration | Noura Al Hashimi | AMBER | Legacy vendor master contains 14% duplicate records; cleansing approach needed before the next mock load. |
| Integration | Arjun Mehta | RED | CargoWise vendor API specification is late; integration build cannot be completed against the final contract. |
| Change & Copilot Adoption | Tom Becker | GREEN | 120 pilot users active on M365 Copilot (600 licences). Readiness workshop planned for Thu 8 Oct 2026. |
| PMO / Testing | Priya Nair | AMBER | UAT (11–29 Jan 2027) clashes with the ZVQA year-end close. |

Financials: spend to 30 Sep 2026 is AED 3.05m against a plan of AED 2.85m, a variance of AED 0.20m (7.0%). This is AMBER under the charter tolerance (more than 5%). The overspend is mainly additional Design workshops for warehousing and integration. The AED 0.6m contingency has not been used. The fixed fee remains AED 7.8m.

# 4. Key issues discussed

## 4.1 CargoWise integration (RED)

Arjun Mehta reported that the CargoWise vendor has not delivered the final API specification, which was due on Fri 28 Aug 2026. The team is building against the draft specification with mock services, but cannot finish the shipment and billing interfaces. Ravi Kumar agreed that Zava, as the contract holder, will escalate formally to the vendor.

## 4.2 ZATCA e-invoicing for ZVSA (AMBER)

ZVSA must issue ZATCA-compliant e-invoices from go-live. The design assumes an accredited ISV solution, but no ISV has been selected. James Okafor will bring a shortlist with costs and implementation timelines so that Zava can decide in October.

## 4.3 Vendor master duplicates (AMBER)

Noura Al Hashimi reported that 14% of legacy vendor master records across Dynamics GP 2018 and Tally are duplicates. Hassan Ali agreed that Zava finance will cleanse duplicates in the source systems before the next mock migration, using match rules supplied by Frontier.

## 4.4 UAT and the ZVQA year-end close (AMBER)

The ZVQA finance team will be closing the year during the UAT window. Hassan Ali will prepare a resourcing plan for ZVQA UAT, including backfill options, rather than moving the UAT dates.

## 4.5 Warehouse mobile devices (AMBER)

Rahul Verma explained that the choice of handheld devices for the warehouse mobile app is needed by mid-October to keep Sprint 5 on track. Grace Lee will confirm the device decision after the device trial at the Jebel Ali warehouse.

# 5. Decisions

| Ref | Decision |
| --- | --- |
| D-0930-01 | The go-live date of Mon 1 Mar 2027 and cutover weekend of Fri 26–Sun 28 Feb 2027 are reaffirmed. No re-baseline at this stage. |
| D-0930-02 | Zava will escalate the late CargoWise API specification formally to the vendor. Integration continues against the draft specification with mock services. |
| D-0930-03 | Vendor master duplicates will be cleansed in the source systems by Zava finance before the next mock migration. |
| D-0930-04 | The spend variance of 7.0% is accepted as AMBER. The PMO will present a forecast to complete at the October SteerCo. |
| D-0930-05 | Change requests arising from Build (ZVQA intercompany settlement, customer shipment tracking, rate-card engine) will be submitted formally for decision at the SteerCo on Wed 28 Oct 2026. |

# 6. Actions

Status as updated by the PMO on Fri 16 Oct 2026.

| Ref | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A-0930-01 | Send a formal escalation letter to the CargoWise vendor about the late API specification. | Ravi Kumar | Fri 9 Oct 2026 | Open |
| A-0930-02 | Present a shortlist of ZATCA e-invoicing ISVs for ZVSA, with costs and implementation timelines. | James Okafor | Wed 14 Oct 2026 | Open |
| A-0930-03 | Prepare the UAT resourcing plan for ZVQA, covering the clash with the year-end close. | Hassan Ali | Wed 21 Oct 2026 | Open |
| A-0930-04 | Confirm the warehouse mobile device decision after the device trial. | Grace Lee | Fri 16 Oct 2026 | Open |
| A-0930-05 | Share the vendor master duplicate analysis and match rules with Zava finance. | Noura Al Hashimi | Wed 7 Oct 2026 | Closed (completed Tue 6 Oct 2026) |
| A-0930-06 | Propose the Copilot champions network structure and nomination approach. | Tom Becker | Fri 6 Nov 2026 | Open |

# 7. Any other business

Tom Becker gave a short update on M365 Copilot: 120 pilot users are active out of 600 licences. A readiness workshop with Ravi Kumar and Elena Petrova is planned for Thu 8 Oct 2026 to review data access, information protection and adoption. Findings will be reported to the October SteerCo.

The next SteerCo is on Wed 28 Oct 2026, 10:00–11:30. The meeting closed at 11:35.

Fictitious test data – Copilot for Frontier Consultancy scenario testing