## Read me
Frontier Bid Pipeline and Capacity
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Item | Detail
Purpose | Frontier Consulting's active bid pipeline, architect capacity and past win/loss record (Business Applications practice, owner Lorette Roos; bid manager Sara Haddad). Used in test scenarios where Copilot assesses go/no-go, bid resourcing and capacity risk for the Zava bid (ZAV-RFP-2026-014, due Mon 9 Nov 2026 12:00).
Test-data notice | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious.
As at | Monday 19 Oct 2026 (Dubai, UTC+4). Currency AED excl. VAT.
Key capacity finding | Omar Khalil (Lead Solution Architect) is over-allocated in the weeks commencing 26 Oct and 2 Nov 2026 – see Architect Capacity.
Sheet map
Bid Pipeline | 12 active pursuits with value, products, due date, bid manager, architect, win probability, weighted value (formula) and status. Zava row highlighted.
Architect Capacity | Days allocated per week (5 Oct – 28 Dec 2026) for Omar Khalil, James Okafor, Lina Mansour, Rahul Verma and Arjun Mehta; totals and utilisation by formula; >100% highlighted red.
Win-Loss History | 20 decided bids with outcome, primary reason, competitor and lesson learned; win-rate summary by formula.
Fictitious test data – Copilot for Frontier Consultancy scenario testing

## Bid Pipeline
Frontier Consulting – active bid pipeline (as at Mon 19 Oct 2026)
Business Applications practice · Values in AED excl. VAT · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Bid ID | Customer | Customer RFP / ref | Value AED | Products | Due date | Bid manager | Architect | Win probability | Weighted value AED | Status
FC-BID-2026-031 | Zava LLC | ZAV-RFP-2026-014 | 9800000 | D365 Sales, D365 Customer Service, Customer Insights – Journeys, D365 Finance & SCM, Power BI, integrations | 2026-11-09 | Sara Haddad | Omar Khalil (lead), James Okafor (Finance & SCM) | 40% | 3920000 | Response in preparation – clarifications due 22 Oct 17:00; response due 9 Nov 12:00
FC-BID-2026-027 | Zava Trading Middle East | ZAV-CS-2026-03 | 1850000 | D365 Customer Service, D365 Contact Center | 2026-10-30 | Sara Haddad | Omar Khalil | 50% | 925000 | Response in preparation
FC-BID-2026-028 | Zava Banking Gulf | ZAV-PP-0921 | 1200000 | Power Platform CoE, Copilot Studio agents | 2026-11-04 | Lorette Roos | Omar Khalil | 35% | 420000 | Response in preparation
FC-BID-2026-029 | Zava LLC | ZAV-HZN CR-007 | 108000 | D365 Finance – intercompany auto-settlement for ZVQA (18 days) | 2026-10-30 | Priya Nair | James Okafor | 80% | 86400 | Change request estimate in review
FC-BID-2026-030 | Zava LLC | ZAV-HZN CR-008 | 250000 | Power Pages customer portal for shipment tracking (45 days) | 2026-11-06 | Priya Nair | Arjun Mehta | 70% | 175000 | Change request estimate in preparation
FC-BID-2026-024 | Zava Telecom | ZAV-RFP-2026-07 | 2750000 | D365 Contact Center, Copilot Studio | 2026-10-12 | Sara Haddad | Omar Khalil | 45% | 1237500 | Submitted 12 Oct – awaiting shortlist
FC-BID-2026-032 | Zava Leisure & Resorts | ZAV-CRM-2026 | 950000 | D365 Sales, Customer Insights – Journeys | 2026-11-13 | Sara Haddad | Lina Mansour | 30% | 285000 | RFP received – go/no-go 21 Oct
FC-BID-2026-033 | Zava Healthcare Group | ZAV-COP-01 | 780000 | M365 Copilot adoption (1,000 licences), Copilot Studio | 2026-10-27 | Lorette Roos | Lina Mansour | 55% | 429000 | Response in preparation
FC-BID-2026-034 | Zava Aviation Services | ZAV-ERP-2026-02 | 4600000 | D365 Finance & SCM, Power BI | 2026-11-20 | Sara Haddad | James Okafor | 30% | 1380000 | RFP received
FC-BID-2026-035 | Zava Industries KSA | ZAV-FIN-118 | 3100000 | D365 Finance, ZATCA e-invoicing | 2026-11-23 | Sara Haddad | James Okafor | 35% | 1085000 | RFP received
FC-BID-2026-036 | Zava Importers Oman | ZAV-OM-2026 | 2300000 | D365 Finance & SCM (upgrade from Business Central) | 2026-12-01 | Sara Haddad | James Okafor, Rahul Verma | 25% | 575000 | Qualifying – RFP expected 26 Oct
FC-BID-2026-037 | Zava Coffee Arabia | ZAV-RFI-09 | 1400000 | D365 Sales, D365 Field Service | 2026-12-07 | Sara Haddad | Omar Khalil | 30% | 420000 | Qualifying – RFI submitted
Total | 12 bids |  | 29088000 |  |  |  |  | 37.6% | 10937900

## Architect Capacity
Architect & solution-lead capacity by week – Oct to Dec 2026 (days)
Week commencing Monday · Capacity = 5 days less public holidays (UAE National Day week 30 Nov: 3 days; week 28 Dec: 4 days) and planned leave · Utilisation > 100% = over-allocated · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Person | Allocation | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | Q4 total (days) | Weeks over 100%
Omar Khalil | Zava Horizon (ZAV-HZN) – CE design authority | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1.5 | 1.5 | 0.5 | 0 | 16.5
Omar Khalil | Zava ZAV-RFP-2026-014 bid | 0 | 1 | 2 | 4 | 4 | 1 | 1 | 2 | 0.5 | 0.5 | 0.5 | 0 | 0 | 16.5
Omar Khalil | Other bids & orals | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 | 1 | 1 | 1 | 1.5 | 0.5 | 0 | 0 | 12.5
Omar Khalil | Practice / internal | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
Omar Khalil | Total allocated | 4 | 4.5 | 5 | 7.5 | 7 | 3.5 | 4 | 5 | 3 | 4 | 3 | 1 | 0.5 | 52
Omar Khalil | Capacity (days) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 4 | 62
Omar Khalil | Utilisation % | 80% | 90% | 100% | 150% | 140% | 70% | 80% | 100% | 100% | 80% | 60% | 20% | 12.5% | 83.87% | 2
James Okafor | Zava Horizon (ZAV-HZN) – Finance workstream | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 0 | 33
James Okafor | Zava ZAV-RFP-2026-014 bid | 0 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 4.5
James Okafor | Other bids & orals | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 7.5
James Okafor | Practice / internal | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
James Okafor | Total allocated | 4 | 4.5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | 4 | 1.5 | 0.5 | 51.5
James Okafor | Capacity (days) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 2 | 0 | 55
James Okafor | Utilisation % | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 80% | 75% | 0% | 93.64% | 0
Lina Mansour | Zava Horizon (ZAV-HZN) – Sales & Service CE | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 1 | 0 | 33
Lina Mansour | Zava ZAV-RFP-2026-014 bid | 0 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5
Lina Mansour | Other bids & orals | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 6.5
Lina Mansour | Practice / internal | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
Lina Mansour | Total allocated | 4 | 4.5 | 5 | 5 | 5 | 5 | 4.5 | 5 | 3 | 4 | 4 | 1.5 | 0.5 | 51
Lina Mansour | Capacity (days) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 0 | 58
Lina Mansour | Utilisation % | 80% | 90% | 100% | 100% | 100% | 100% | 90% | 100% | 100% | 80% | 80% | 30% | 0% | 87.93% | 0
Rahul Verma | Zava Horizon (ZAV-HZN) – Supply Chain & Warehousing | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2.5 | 3.5 | 3.5 | 1 | 0 | 38.5
Rahul Verma | Zava ZAV-RFP-2026-014 bid | 0 | 0 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Rahul Verma | Other bids & orals | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0 | 2
Rahul Verma | Practice / internal | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
Rahul Verma | Total allocated | 4 | 4 | 4.5 | 5 | 5 | 4 | 4.5 | 4.5 | 3 | 4.5 | 4.5 | 1.5 | 0.5 | 49.5
Rahul Verma | Capacity (days) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 3 | 0 | 56
Rahul Verma | Utilisation % | 80% | 80% | 90% | 100% | 100% | 80% | 90% | 90% | 100% | 90% | 90% | 50% | 0% | 88.39% | 0
Arjun Mehta | Zava Horizon (ZAV-HZN) – Integration (CargoWise) | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2.5 | 3.5 | 3.5 | 1 | 0 | 38.5
Arjun Mehta | Zava ZAV-RFP-2026-014 bid | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
Arjun Mehta | Other bids & orals | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Arjun Mehta | Practice / internal | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
Arjun Mehta | Total allocated | 4 | 4.5 | 5 | 5 | 5 | 4.5 | 4 | 4 | 3 | 4 | 4 | 1.5 | 0.5 | 49
Arjun Mehta | Capacity (days) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 0 | 58
Arjun Mehta | Utilisation % | 80% | 90% | 100% | 100% | 100% | 90% | 80% | 80% | 100% | 80% | 80% | 30% | 0% | 84.48% | 0
Note | Omar Khalil is over-allocated in the weeks of 26 Oct and 2 Nov 2026 (Zava ZAV-RFP-2026-014 response writing overlaps Zava Trading Middle East and Zava Banking Gulf submissions and Zava design authority).

## Win-Loss History
Past bids – win/loss record with reasons (last 20 decided bids)
Values in AED excl. VAT · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Bid ID | Customer | Products | Value AED | Submitted | Decision date | Outcome | Primary reason | Competitor / winner | Lesson learned
FC-BID-2024-019 | Zava Industrial Distribution LLC | D365 Sales, Customer Service, Finance | 5200000 | 2024-11-04 | 2024-12-09 | Won | Strong distribution references and scripted demo of quote-to-cash | — | Scripted demo built on customer's own data was decisive
FC-BID-2025-002 | Zava Winery & Foods Gulf | D365 Finance & SCM | 3800000 | 2025-01-20 | 2025-03-03 | Lost | Price – 18% above winning bid | Global SI | Fixed price too cautious on data migration contingency
FC-BID-2025-004 | Zava LLC | D365 F&O, Sales, Customer Service, M365 Copilot | 7800000 | 2025-12-01 | 2026-04-15 | Won | Multi-entity GCC finance expertise and named team | — | Became programme Zava Horizon (ZAV-HZN)
FC-BID-2025-006 | Zava Healthcare Clinics | D365 Customer Service | 1300000 | 2025-02-10 | 2025-03-24 | Lost | Incumbent relationship – customer extended existing CRM | Incumbent vendor | Qualify incumbent risk harder at go/no-go
FC-BID-2025-008 | Zava Retail ME | D365 Sales, Customer Insights – Journeys | 1650000 | 2025-03-03 | 2025-04-14 | Won | Best marketing consent & journeys demo | — | Arabic journey templates shown live
FC-BID-2025-010 | Zava Research Labs | Power Platform, Copilot Studio | 640000 | 2025-03-17 | 2025-04-21 | Won | Speed – POC delivered in 2 weeks | — | Fast POC is a differentiator for Power Platform
FC-BID-2025-012 | Zava Insurance Gulf | D365 Customer Service, Contact Center | 2900000 | 2025-04-07 | 2025-05-26 | Lost | Functional fit – no native WhatsApp SLA handling shown | Specialist CX partner | Prepare WhatsApp channel demo and SLA workaround
FC-BID-2025-014 | Zava Manufacturing KSA | D365 Finance & SCM, ZATCA | 4300000 | 2025-05-05 | 2025-06-30 | Lost | Local KSA presence and ZATCA references | Saudi-based partner | Need KSA ZATCA reference before next KSA bid
FC-BID-2025-016 | Zava Publishing | M365 Copilot adoption | 420000 | 2025-05-19 | 2025-06-16 | Won | Adoption methodology and change team (Tom Becker) | — | Copilot adoption offer resonates
FC-BID-2025-018 | Zava Corporate Services Gulf | D365 Sales | 880000 | 2025-06-09 | 2025-07-14 | Lost | Price | Offshore delivery partner | Consider blended onshore/offshore rate card
FC-BID-2025-021 | Zava Airlines Cargo | D365 Finance, Power BI | 2100000 | 2025-07-07 | 2025-08-25 | Lost | Team availability – proposed architect not available until Q1 | Global SI | Capacity conflicts on architects cost the bid
FC-BID-2025-023 | Zava Design Institute | D365 Sales, Customer Service | 760000 | 2025-08-04 | 2025-09-08 | Won | Fixed price and fast start | — | Small CE projects win on certainty
FC-BID-2025-026 | Zava Construction Supplies | D365 Sales, Finance & SCM, rental | 3600000 | 2025-09-01 | 2025-10-20 | Lost | Functional fit – rental management and telematics billing gap | ISV-led partner with rental solution | Partner with a rental ISV for equipment-rental bids
FC-BID-2025-029 | Zava Courier Services | D365 Customer Service, Copilot Studio | 1150000 | 2025-10-06 | 2025-11-17 | Won | Copilot agent demo and CSAT case study | — | AI-first demo scored highest
FC-BID-2025-031 | Zava College | Dynamics 365 Sales, Power Pages | 520000 | 2025-11-03 | 2025-12-08 | Lost | Customer chose not to proceed (budget) | No award | —
FC-BID-2026-003 | Zava Travel Group | D365 Sales, Customer Insights – Journeys | 1240000 | 2026-01-12 | 2026-02-23 | Won | Arabic RTL marketing content and consent approach | — | Bilingual capability is a differentiator
FC-BID-2026-006 | Zava Toys Distribution | D365 Finance & SCM | 2650000 | 2026-02-09 | 2026-03-30 | Lost | Price – estimate 22% higher than winner, driven by integrations and data migration | Global SI | Historical overruns made us pad integrations; benchmark with actuals
FC-BID-2026-009 | Zava Architects | Power Platform, M365 Copilot | 380000 | 2026-03-09 | 2026-04-13 | Won | Existing M365 relationship | — | Cross-sell from M365 base
FC-BID-2026-012 | Zava Building Materials | D365 Sales, Customer Service, Finance | 4900000 | 2026-05-04 | 2026-06-22 | Lost | Late, incomplete clarification questions; weak functional-fit response | Global SI | Start Appendix A responses in week 1; submit clarifications on time
FC-BID-2026-015 | Zava Pharmaceuticals ME | D365 Customer Service | 990000 | 2026-06-15 | 2026-07-27 | Won | SLA design and Copilot case summarisation | — | Reusable service accelerator
Summary | Count | Value AED
Won | 10 | 20230000
Lost | 10 | 26950000
Total decided | 20 | 47180000
Win rate (by count) | 50%
Win rate (by value) |  | 42.88%