## Read me
ZAV-HZN RAID Log
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Purpose | Risks, Assumptions, Issues and Dependencies register for the Zava Horizon programme. Use for testing Copilot Cowork scenarios such as RAID summaries, stale-item chasing, overdue reviews and SteerCo preparation.
Programme | Zava Horizon (ZAV-HZN) – Zava LLC, delivered by Frontier Consulting
Data as of | Monday 19 Oct 2026 (Dubai, UTC+4)
As-of date (used in formulas) | 2026-10-19
Currency | AED
Prepared by | Priya Nair, Project Manager (Frontier Consulting) – scenario owner Lorette Roos
Sheet | Contents
RAID Log | 36 RAID entries with owner, dates, probability/impact, RAG, status and mitigation. 'Days since update' and 'Stale / overdue flag' are calculated against the as-of date above.
Summary | Counts by type, RAG and status, plus stale and overdue counts (formulas).
Rules | Stale = open item not updated for more than 21 days. Overdue = open item with due date before the as-of date.
Important | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious and must not be used for real decisions.

## RAID Log
ZAV-HZN RAID Log ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
ID | Type | Title | Description | Workstream | Owner | Raised date | Due date | Probability | Impact | RAG | Status | Mitigation/Next step | Last updated | Days since update | Stale / overdue flag
R-001 | Risk | CargoWise API delay pushes Integration build into SIT | Late vendor API specification means CargoWise shipment and invoice interfaces cannot be completed in Build; risk that SIT (30 Nov–18 Dec) starts without end-to-end freight flows. | Integration | Arjun Mehta | 2026-09-15 | 2026-10-30 | High | High | RED | Open | Escalated to CargoWise account manager via Ravi Kumar; build against draft spec with mock service; re-plan Sprint 5 if spec not received by 23 Oct. | 2026-10-16 | 3
R-002 | Risk | Reduced Finance SME availability during UAT | UAT (11–29 Jan 2027) overlaps ZVQA year-end close; Hassan Ali's team may not be able to execute finance UAT scripts. | PMO | Priya Nair | 2026-09-22 | 2026-11-06 | Medium | High | AMBER | Open | Options paper for SteerCo 28 Oct: split UAT into two waves or bring ZVQA scripts forward to SIT week 3. | 2026-10-13 | 6
R-003 | Risk | ZATCA e-invoicing ISV not selected in time for ZVSA SIT | Without an ISV decision the ZVSA e-invoicing connector cannot be configured or tested before SIT; compliance risk at go-live. | Finance | James Okafor | 2026-09-01 | 2026-10-09 | High | High | AMBER | Open | Shortlist of two ISVs issued to Nadia Farouk; decision requested. | 2026-09-22 | 27 | Overdue & stale
R-004 | Risk | Vendor master duplicates inflate migration volume | 14% duplicate vendors in legacy GP 2018 and Tally risk duplicate payments and failed migration loads. | Data Migration | Noura Al Hashimi | 2026-09-08 | 2026-10-31 | Medium | High | AMBER | Open | De-duplication rules agreed; Hassan Ali's team to confirm golden records by entity. | 2026-10-14 | 5
R-005 | Risk | Warehouse mobile device decision delays WMS testing | No decision on handheld devices; warehouse mobile app flows cannot be tested on target hardware. | Supply Chain/Warehousing | Rahul Verma | 2026-09-10 | 2026-10-02 | Medium | Medium | AMBER | Open | Device comparison sent to Grace Lee; awaiting decision. | 2026-09-18 | 31 | Overdue & stale
R-006 | Risk | Programme spend ahead of plan | Spend to 30 Sep 2026 is AED 3.05m against plan of AED 2.85m (+7.0%); continued overrun would draw down the AED 0.6m contingency early. | PMO | Priya Nair | 2026-10-05 | 2026-10-28 | Medium | High | AMBER | Open | Forecast to complete re-baselined; contingency drawdown request for CargoWise rework to SteerCo 28 Oct. | 2026-10-15 | 4
R-007 | Risk | Group Financial Controller time split with BAU | Hassan Ali is splitting time between BAU month-end and design walkthroughs; finance decisions are slowing. | Finance | James Okafor | 2026-08-18 | 2026-09-25 | Medium | Medium | AMBER | Open | Request a delegate from Hassan Ali's team for day-to-day decisions. | 2026-08-25 | 55 | Overdue & stale
R-008 | Risk | Copilot adoption stalls beyond the pilot group | Weekly active usage outside the 120 pilot users may stay low once the 600 licences are assigned. | Change & Copilot Adoption | Tom Becker | 2026-09-29 | 2026-11-13 | Medium | Medium | GREEN | Open | Champions network by department; persona-based training wave 2. | 2026-10-12 | 7
R-009 | Risk | Oversharing exposes sensitive content through Copilot | SharePoint readiness scan flags 37 of 60 sites shared with 'Everyone except external users', including HR-Payroll and Finance-Board. | Change & Copilot Adoption | Tom Becker | 2026-10-06 | 2026-10-23 | High | High | AMBER | Open | Remove EEEU permissions on flagged sites; apply sensitivity labels; restricted SharePoint search for HR and Finance sites. | 2026-10-16 | 3
R-010 | Risk | Pricing accuracy risk from CR-009 | Replacing the bespoke rate-card engine with standard trade agreements saves 12 days but may not reproduce all surcharge rules. | Sales & Service CE | Lina Mansour | 2026-10-07 | 2026-10-28 | Medium | High | AMBER | Open | Run 200 historical quotes through trade agreements and compare before SteerCo decision. | 2026-10-14 | 5
R-011 | Risk | Tally (KSA) extraction quality for opening balances | Tally exports for ZVSA lack dimension detail; opening balance load may need manual mapping. | Data Migration | Noura Al Hashimi | 2026-08-20 | 2026-10-15 | Medium | Medium | GREEN | Open | Mapping workbook with ZVSA finance team. | 2026-09-03 | 46 | Overdue & stale
R-012 | Risk | Case queue design misaligned with shift model | Customer Service queues did not reflect Samir Haddad's three-shift model. | Sales & Service CE | Lina Mansour | 2026-08-25 | 2026-09-18 | Low | Medium | GREEN | Closed | Queue design reworked and signed off by Samir Haddad. | 2026-09-18
R-013 | Risk | Hypercare overlaps Ramadan 2027 | Ramadan (expected mid-Feb to mid-Mar 2027) reduces working hours during cutover and hypercare. | PMO | Priya Nair | 2026-10-12 | 2026-11-27 | Medium | Medium | AMBER | Open | Agree reduced-hours hypercare rota with Elena Petrova; extend hypercare support desk hours. | 2026-10-12 | 7
R-014 | Risk | Intercompany posting performance across five entities | High intercompany volumes between ZVAE, ZVSA, ZVOM, ZVQA and ZVHQ may breach batch windows. | Finance | James Okafor | 2026-09-02 | 2026-11-30 | Low | High | GREEN | Open | Performance test in SIT with production-like volumes. | 2026-09-29 | 20
A-001 | Assumption | Zava SMEs available 3 days a week during Build | Each workstream has a named Zava SME for at least 3 days a week until end of Build. | PMO | Priya Nair | 2026-06-10 | 2026-11-27 | Medium | High | GREEN | Open | Track SME attendance in PMO status. | 2026-10-01 | 18
A-002 | Assumption | CargoWise vendor delivers final API spec by 23 Oct 2026 | Integration re-plan assumes final spec by end of Sprint 4. | Integration | Arjun Mehta | 2026-09-30 | 2026-10-23 | High | High | AMBER | Open | Daily chase; fallback plan is file-based interface for go-live. | 2026-10-16 | 3
A-003 | Assumption | Standard trade agreements cover about 90% of rate-card scenarios | Basis for the CR-009 estimate of 12 days saved. | Supply Chain/Warehousing | Rahul Verma | 2026-10-07 | 2026-10-28 | Medium | High | AMBER | Open | Validate with quote sample (see R-010). | 2026-10-07 | 12
A-004 | Assumption | Opening balances migrated at trial-balance level | No open-item history older than 2 years will be migrated. | Finance | James Okafor | 2026-07-15 | 2026-09-04 | Low | Medium | GREEN | Closed | Confirmed in design sign-off 4 Sep 2026. | 2026-09-04
A-005 | Assumption | All 600 Copilot licences assigned before training wave 2 | Training wave 2 assumes licences are assigned to all target users. | Change & Copilot Adoption | Tom Becker | 2026-09-01 | 2026-09-30 | Medium | Medium | GREEN | Open | Confirm assignment report with Ravi Kumar. | 2026-09-10 | 39 | Overdue & stale
A-006 | Assumption | Azure integration environment provisioned by Zava IT | Logic Apps, Service Bus and Key Vault provisioned by Ravi Kumar's team. | Integration | Arjun Mehta | 2026-08-20 | 2026-09-18 | Medium | High | AMBER | Open | Raise with Ravi Kumar at PMO status. | 2026-09-22 | 27 | Overdue & stale
A-007 | Assumption | Single go-live wave for all five legal entities | Go-live on Mon 1 Mar 2027 for ZVAE, ZVSA, ZVOM, ZVQA and ZVHQ together. | PMO | Priya Nair | 2026-06-10 | 2027-02-26 | Low | High | GREEN | Open | Revisit at SteerCo if ZVQA year-end impact grows. | 2026-09-04 | 45 | Stale
I-001 | Issue | CargoWise integration delayed – vendor API spec late | Vendor API specification is late; shipment, job costing and invoice interfaces blocked. Six Sprint 4 backlog items are blocked. | Integration | Arjun Mehta | 2026-09-29 | 2026-10-23 | High | High | RED | Open | Escalation letter to vendor; mock service build; decision at SteerCo 28 Oct on file-based fallback. | 2026-10-16 | 3
I-002 | Issue | ZATCA e-invoicing ISV decision outstanding for ZVSA | ISV decision needed to configure ZVSA e-invoicing (Phase 2 integration). | Finance | James Okafor | 2026-09-15 | 2026-10-14 | High | High | AMBER | Open | Decision paper with Nadia Farouk; add to SteerCo agenda. | 2026-10-14 | 5 | Overdue
I-003 | Issue | Legacy vendor master has 14% duplicates | Profiling of GP 2018 and Tally vendor master found 14% duplicates across entities. | Data Migration | Noura Al Hashimi | 2026-09-22 | 2026-10-30 | Medium | High | AMBER | Open | Cleansing in progress; dedup trial load in Sprint 5. | 2026-10-15 | 4
I-004 | Issue | UAT clashes with ZVQA year-end close | UAT window 11–29 Jan 2027 overlaps ZVQA year-end close activities. | PMO | Priya Nair | 2026-10-06 | 2026-10-28 | Medium | High | AMBER | Open | Options to SteerCo 28 Oct. | 2026-10-15 | 4
I-005 | Issue | Warehouse mobile device decision outstanding | Handheld scanner model not selected; blocks WMS mobile testing and device procurement lead time (8 weeks). | Supply Chain/Warehousing | Rahul Verma | 2026-09-17 | 2026-10-09 | Medium | High | AMBER | Open | Grace Lee to decide; escalate to Ravi Kumar if no decision. | 2026-09-24 | 25 | Overdue & stale
I-006 | Issue | Sprint 4 velocity reduced by CargoWise blockers | Sprint 4 is about 70% complete with six items blocked by CargoWise. | PMO | Priya Nair | 2026-10-13 | 2026-10-23 | Medium | Medium | AMBER | Open | Pull forward Sprint 5 Finance stories; carry blocked items. | 2026-10-16 | 3
I-007 | Issue | UAT environment refresh failed | Tier 2 environment refresh from build failed due to storage capacity. | Integration | Arjun Mehta | 2026-09-21 | 2026-09-25 | Low | Medium | GREEN | Closed | Capacity added; refresh re-run successfully. | 2026-09-25
I-008 | Issue | GP 2018 Qatar chart of accounts mapping incomplete | ZVQA chart of accounts mapping to the new global COA is 60% complete. | Finance | James Okafor | 2026-09-01 | 2026-09-25 | Medium | Medium | AMBER | Open | Workshop with ZVQA finance. | 2026-09-11 | 38 | Overdue & stale
I-009 | Issue | 37 SharePoint sites flagged for oversharing | Copilot readiness scan flagged 37 of 60 sites, including HR-Payroll and Finance-Board. | Change & Copilot Adoption | Tom Becker | 2026-10-08 | 2026-10-30 | Medium | High | AMBER | Open | Site owners notified; remediation tracker started. | 2026-10-15 | 4
D-001 | Dependency | CargoWise vendor API specification | Integration build depends on final API specification from the CargoWise vendor. | Integration | Arjun Mehta | 2026-09-15 | 2026-10-23 | High | High | RED | Open | Chase via Ravi Kumar; escalate at SteerCo. | 2026-10-16 | 3
D-002 | Dependency | ZATCA e-invoicing ISV selection | ZVSA e-invoicing configuration depends on ISV contract. | Finance | James Okafor | 2026-09-15 | 2026-10-14 | High | High | AMBER | Open | Decision requested from Nadia Farouk. | 2026-09-20 | 29 | Overdue & stale
D-003 | Dependency | Zava IT procurement of warehouse mobile devices | Device delivery needed for UAT; 8-week lead time after decision. | Supply Chain/Warehousing | Ravi Kumar | 2026-09-17 | 2026-11-06 | Medium | High | AMBER | Open | Procurement to start on device decision. | 2026-09-17 | 32 | Stale
D-004 | Dependency | House bank payment and statement file formats | Bank integration depends on file specifications from UAE, KSA and Oman house banks. | Finance | James Okafor | 2026-09-08 | 2026-11-13 | Medium | Medium | AMBER | Open | Formats received for UAE; KSA and Oman pending. | 2026-10-08 | 11
D-005 | Dependency | SteerCo decision on CR-007, CR-008 and CR-009 | Sprint 5 and 6 scope depends on SteerCo decisions on 28 Oct. | PMO | Priya Nair | 2026-10-01 | 2026-10-28 | Medium | High | AMBER | Open | CR packs circulated to Nadia Farouk and Ravi Kumar. | 2026-10-15 | 4
D-006 | Dependency | Entra ID groups and Conditional Access for Copilot | Copilot rollout depends on licence groups and Conditional Access policies. | Change & Copilot Adoption | Tom Becker | 2026-09-01 | 2026-09-30 | Low | Medium | GREEN | Closed | Configured by Zava IT. | 2026-09-29

## Summary
ZAV-HZN RAID summary ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Type | Total | Open | RED (open) | AMBER (open) | GREEN (open) | Overdue (open) | Stale (open)
Risk | 14 | 13 | 1 | 9 | 3 | 4 | 4
Assumption | 7 | 6 | 0 | 3 | 3 | 2 | 3
Issue | 9 | 8 | 1 | 7 | 0 | 3 | 2
Dependency | 6 | 5 | 1 | 4 | 0 | 1 | 2
Total | 36 | 32 | 3 | 23 | 6 | 10 | 11
Check: total entries on RAID Log (should equal B7) | 36