## Read me
ZAV-HZN Sprint Backlog Export
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Purpose | Azure DevOps-style work item export for the Zava Horizon Build phase (Sprints 3–5). Use for testing sprint status summaries, blocker analysis (CargoWise), velocity and burndown questions, and stand-up preparation.
Programme | Zava Horizon (ZAV-HZN) – Zava LLC, delivered by Frontier Consulting
Data as of | Monday 19 Oct 2026 (Dubai, UTC+4)
As-of date (used in formulas) | 2026-10-19
Currency | AED
Prepared by | Priya Nair, Project Manager (Frontier Consulting) – scenario owner Lorette Roos
Sheet | Contents
Backlog | 90 work items (Epics, Features, User Stories, Bugs, Tasks) exported from Azure DevOps project ZAV-HZN. Epics and Features sit at release level.
Sprint summary | Story points and item counts by sprint and state, Sprint 4 completion % and blocked counts (formulas).
Sprint calendar | Sprint 3: Mon 28 Sep – Fri 9 Oct 2026 ¦ Sprint 4: Mon 12 Oct – Fri 23 Oct 2026 ¦ Sprint 5: Mon 26 Oct – Fri 6 Nov 2026
Completion rule | Completed = State Resolved or Closed; completion % measured on story points.
Important | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious and must not be used for real decisions.

## Backlog
ZAV-HZN Sprint Backlog Export (Azure DevOps) ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
ID | Work item type | Title | Workstream | Assigned to | State | Sprint | Story points | Remaining work | Tags | Changed date
4101 | Epic | Finance core – GL, AP, AR, fixed assets for five legal entities | Finance | James Okafor | Active | ZAV-HZN\Release 1 |  |  | fin | 2026-10-05 10:12
4102 | Epic | Warehouse management and transport for Jebel Ali operations | Supply Chain/Warehousing | Rahul Verma | Active | ZAV-HZN\Release 1 |  |  | scm | 2026-10-05 10:12
4103 | Epic | Sales and Customer Service on Dynamics 365 CE | Sales & Service CE | Lina Mansour | Active | ZAV-HZN\Release 1 |  |  | ce | 2026-10-05 10:12
4104 | Epic | Data migration from Dynamics GP 2018 and Tally | Data Migration | Noura Al Hashimi | Active | ZAV-HZN\Release 1 |  |  | dm | 2026-10-05 10:12
4105 | Epic | Integrations – CargoWise, banks, ZATCA, Azure Integration Services | Integration | Arjun Mehta | Active | ZAV-HZN\Release 1 |  |  | int | 2026-10-05 10:12
4106 | Epic | M365 Copilot rollout – 600 licences | Change & Copilot Adoption | Tom Becker | Active | ZAV-HZN\Release 1 |  |  | chg | 2026-10-05 10:12
4107 | Feature | Intercompany accounting ZVAE/ZVSA/ZVOM/ZVQA/ZVHQ | Finance | James Okafor | Active | ZAV-HZN\Release 1 |  |  | fin | 2026-10-08 15:40
4108 | Feature | ZATCA e-invoicing for ZVSA | Finance | James Okafor | Active | ZAV-HZN\Release 1 |  |  | fin | 2026-10-08 15:40
4109 | Feature | Bank statement and payment integration | Finance | James Okafor | Active | ZAV-HZN\Release 1 |  |  | fin | 2026-10-08 15:40
4110 | Feature | Mobile warehouse app – receiving and putaway | Supply Chain/Warehousing | Rahul Verma | Active | ZAV-HZN\Release 1 |  |  | scm | 2026-10-08 15:40
4111 | Feature | Trade agreements and freight rate cards | Supply Chain/Warehousing | Rahul Verma | Active | ZAV-HZN\Release 1 |  |  | scm | 2026-10-08 15:40
4112 | Feature | Lead-to-quote for freight forwarding | Sales & Service CE | Lina Mansour | Active | ZAV-HZN\Release 1 |  |  | ce | 2026-10-08 15:40
4113 | Feature | Case management and SLA for customer service | Sales & Service CE | Lina Mansour | Active | ZAV-HZN\Release 1 |  |  | ce | 2026-10-08 15:40
4114 | Feature | Vendor and customer master migration | Data Migration | Noura Al Hashimi | Active | ZAV-HZN\Release 1 |  |  | dm | 2026-10-08 15:40
4115 | Feature | Opening balances and open items | Data Migration | Noura Al Hashimi | New | ZAV-HZN\Release 1 |  |  | dm | 2026-10-08 15:40
4116 | Feature | CargoWise shipment and job costing interface | Integration | Arjun Mehta | Active | ZAV-HZN\Release 1 |  |  | int | 2026-10-08 15:40
4117 | Feature | Integration monitoring and alerting | Integration | Arjun Mehta | New | ZAV-HZN\Release 1 |  |  | int | 2026-10-08 15:40
4118 | Feature | Copilot readiness – SharePoint oversharing remediation | Change & Copilot Adoption | Tom Becker | Active | ZAV-HZN\Release 1 |  |  | chg | 2026-10-08 15:40
4119 | Feature | Copilot persona training and champions | Change & Copilot Adoption | Tom Becker | Active | ZAV-HZN\Release 1 |  |  | chg | 2026-10-08 15:40
4120 | Feature | Financial reporting and Power BI | Finance | James Okafor | New | ZAV-HZN\Release 1 |  |  | fin | 2026-10-08 15:40
4121 | User Story | GL chart of accounts and main account structure for ZVAE | Finance | James Okafor | Closed | ZAV-HZN\Sprint 3 | 5 |  | fin | 2026-10-01 09:00
4122 | User Story | Financial dimensions: entity, department, cost centre, trade lane | Finance | James Okafor | Closed | ZAV-HZN\Sprint 3 | 3 |  | fin | 2026-10-02 10:07
4123 | User Story | AP invoice approval workflow with 3-way match | Finance | James Okafor | Closed | ZAV-HZN\Sprint 3 | 5 |  | fin | 2026-10-03 11:14
4124 | Task | Configure number sequences for five legal entities | Finance | Arjun Mehta | Closed | ZAV-HZN\Sprint 3 |  | 0 | fin | 2026-10-04 12:21
4125 | User Story | Warehouse locations and zones for Jebel Ali DC | Supply Chain/Warehousing | Rahul Verma | Closed | ZAV-HZN\Sprint 3 | 5 |  | scm | 2026-10-05 13:28
4126 | User Story | Inbound receiving by license plate | Supply Chain/Warehousing | Rahul Verma | Closed | ZAV-HZN\Sprint 3 | 8 |  | scm | 2026-10-06 14:35
4127 | Bug | Location directive picks wrong zone for bonded stock | Supply Chain/Warehousing | Rahul Verma | Closed | ZAV-HZN\Sprint 3 | 2 |  | scm | 2026-10-07 15:42
4128 | User Story | Account and contact model for shippers and consignees | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 3 | 3 |  | ce | 2026-10-08 16:49
4129 | User Story | Opportunity stages for freight forwarding deals | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 3 | 3 |  | ce | 2026-10-09 09:56
4130 | User Story | Case categories and queues for three-shift model | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 3 | 5 |  | ce | 2026-10-01 10:03
4131 | Task | SLA KPI configuration for first response | Sales & Service CE | Lina Mansour | Resolved | ZAV-HZN\Sprint 3 |  | 0 | ce | 2026-10-02 11:10
4132 | User Story | Vendor master profiling – GP 2018 and Tally | Data Migration | Noura Al Hashimi | Closed | ZAV-HZN\Sprint 3 | 5 |  | dm | 2026-10-03 12:17
4133 | Task | Data migration framework – staging database | Data Migration | Noura Al Hashimi | Closed | ZAV-HZN\Sprint 3 |  | 0 | dm | 2026-10-04 13:24
4134 | User Story | Customer master mapping template | Data Migration | Noura Al Hashimi | Closed | ZAV-HZN\Sprint 3 | 3 |  | dm | 2026-10-05 14:31
4135 | User Story | Azure Service Bus topics and subscriptions | Integration | Arjun Mehta | Closed | ZAV-HZN\Sprint 3 | 5 |  | int | 2026-10-06 15:38
4136 | Task | Key Vault and managed identity setup | Integration | Arjun Mehta | Closed | ZAV-HZN\Sprint 3 |  | 0 | int | 2026-10-07 16:45
4137 | User Story | CargoWise interface design (draft spec) | Integration | Arjun Mehta | Resolved | ZAV-HZN\Sprint 3 | 5 |  | int | 2026-10-08 09:52
4138 | User Story | Copilot pilot onboarding – 120 users | Change & Copilot Adoption | Tom Becker | Closed | ZAV-HZN\Sprint 3 | 3 |  | chg | 2026-10-09 10:59
4139 | User Story | SharePoint oversharing scan – 60 sites | Change & Copilot Adoption | Tom Becker | Closed | ZAV-HZN\Sprint 3 | 3 |  | chg | 2026-10-01 11:06
4140 | Bug | Posting profile error on ZVOM vendor invoices | Finance | James Okafor | Closed | ZAV-HZN\Sprint 3 | 2 |  | fin | 2026-10-02 12:13
4141 | Task | Sprint 3 demo and retrospective | Finance | Priya Nair | Closed | ZAV-HZN\Sprint 3 |  | 0 | fin | 2026-10-03 13:20
4142 | User Story | Fixed asset groups and depreciation profiles | Finance | James Okafor | Closed | ZAV-HZN\Sprint 3 | 5 |  | fin | 2026-10-04 14:27
4143 | User Story | Intercompany journal auto-posting ZVAE to ZVSA | Finance | James Okafor | Closed | ZAV-HZN\Sprint 4 | 8 | 0 | fin; intercompany | 2026-10-12 09:00
4144 | User Story | Intercompany due-to/due-from settlement rules | Finance | James Okafor | Closed | ZAV-HZN\Sprint 4 | 5 | 0 | fin; intercompany | 2026-10-13 10:13
4145 | User Story | AR customer invoicing with freight charge codes | Finance | James Okafor | Closed | ZAV-HZN\Sprint 4 | 8 | 0 | fin | 2026-10-14 11:26
4146 | User Story | Bank reconciliation – UAE statement import | Finance | James Okafor | Resolved | ZAV-HZN\Sprint 4 | 5 | 0 | fin; banking | 2026-10-15 12:39
4147 | Bug | Exchange rate revaluation posts to wrong account (ZVQA) | Finance | James Okafor | Closed | ZAV-HZN\Sprint 4 | 2 | 0 | fin; ZVQA | 2026-10-16 13:52
4148 | User Story | Wave picking for outbound shipments | Supply Chain/Warehousing | Rahul Verma | Closed | ZAV-HZN\Sprint 4 | 8 | 0 | scm; WMS | 2026-10-16 14:05
4149 | User Story | Cycle counting by zone | Supply Chain/Warehousing | Rahul Verma | Resolved | ZAV-HZN\Sprint 4 | 5 | 0 | scm; WMS | 2026-10-16 15:18
4150 | User Story | Trade agreement journals for standard freight rates | Supply Chain/Warehousing | Rahul Verma | Closed | ZAV-HZN\Sprint 4 | 5 | 0 | scm; CR-009 | 2026-10-19 16:31
4151 | User Story | Quote template with freight rate lines | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 4 | 5 | 0 | ce | 2026-10-12 17:44
4152 | User Story | Case routing by entity and language (Arabic/English) | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 4 | 5 | 0 | ce | 2026-10-13 09:57
4153 | User Story | SLA escalation to Customer Service Manager | Sales & Service CE | Lina Mansour | Closed | ZAV-HZN\Sprint 4 | 3 | 0 | ce | 2026-10-14 10:10
4154 | User Story | Vendor de-duplication rules (14% duplicates) | Data Migration | Noura Al Hashimi | Closed | ZAV-HZN\Sprint 4 | 5 | 0 | dm; vendor-dedup | 2026-10-15 11:23
4155 | User Story | Customer master trial load 1 | Data Migration | Noura Al Hashimi | Resolved | ZAV-HZN\Sprint 4 | 3 | 0 | dm; trial-load | 2026-10-16 12:36
4156 | Bug | Trial load rejects Arabic characters in vendor names | Data Migration | Noura Al Hashimi | Closed | ZAV-HZN\Sprint 4 | 1 | 0 | dm; trial-load | 2026-10-16 13:49
4157 | User Story | Copilot prompt gallery for Finance analyst persona | Change & Copilot Adoption | Tom Becker | Closed | ZAV-HZN\Sprint 4 | 2 | 0 | chg; copilot | 2026-10-16 14:02
4158 | User Story | Mobile app receiving on handheld | Supply Chain/Warehousing | Rahul Verma | Active | ZAV-HZN\Sprint 4 | 3 |  | scm; WMS; device-decision | 2026-10-19 15:15
4159 | User Story | Power BI finance dataset – trial balance | Finance | James Okafor | Active | ZAV-HZN\Sprint 4 | 2 |  | fin; reporting | 2026-10-12 16:28
4160 | Bug | Case SLA timer pauses incorrectly on weekends | Sales & Service CE | Lina Mansour | Active | ZAV-HZN\Sprint 4 | 1 |  | ce | 2026-10-13 17:41
4161 | User Story | Remove EEEU permissions on flagged SharePoint sites | Change & Copilot Adoption | Tom Becker | New | ZAV-HZN\Sprint 4 | 3 |  | chg; copilot; oversharing | 2026-10-14 09:54
4162 | User Story | Copilot champions network setup | Change & Copilot Adoption | Tom Becker | New | ZAV-HZN\Sprint 4 | 3 |  | chg; copilot | 2026-10-15 10:07
4163 | User Story | CargoWise shipment event inbound interface | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 | 5 |  | int; CargoWise; Blocked; vendor-spec | 2026-10-16 12:40
4164 | User Story | CargoWise job costing to F&O project accounting | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 | 5 |  | int; CargoWise; Blocked; vendor-spec | 2026-10-14 13:51
4165 | User Story | CargoWise AR invoice sync to D365 Finance | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 | 5 |  | int; CargoWise; Blocked; vendor-spec | 2026-10-15 14:02
4166 | User Story | Customer account sync D365 CE to CargoWise | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 | 3 |  | int; CargoWise; Blocked; vendor-spec | 2026-10-16 15:13
4167 | Task | Build CargoWise API mock service | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 |  | 16 | int; CargoWise; Blocked | 2026-10-14 10:24
4168 | Task | CargoWise error handling and retry policy | Integration | Arjun Mehta | Blocked | ZAV-HZN\Sprint 4 |  | 12 | int; CargoWise; Blocked | 2026-10-15 11:35
4169 | Task | Bank payment file format – KSA | Finance | Arjun Mehta | Active | ZAV-HZN\Sprint 4 |  | 6 | fin; banking | 2026-10-14 17:38
4170 | Task | Sprint 4 demo preparation | Finance | Priya Nair | New | ZAV-HZN\Sprint 4 |  | 4 | fin | 2026-10-15 09:51
4171 | User Story | ZATCA e-invoicing connector configuration (pending ISV) | Finance | James Okafor | New | ZAV-HZN\Sprint 5 | 5 |  | fin; ZATCA; ZVSA | 2026-10-05 09:00
4172 | User Story | Intercompany auto-settlement for ZVQA (CR-007, pending approval) | Finance | James Okafor | New | ZAV-HZN\Sprint 5 | 8 |  | fin; CR-007; ZVQA | 2026-10-06 10:17
4173 | User Story | Fixed asset migration template | Finance | James Okafor | New | ZAV-HZN\Sprint 5 | 3 |  | fin | 2026-10-07 11:34
4174 | User Story | Vendor payment proposal and approval | Finance | James Okafor | New | ZAV-HZN\Sprint 5 | 5 |  | fin | 2026-10-08 12:51
4175 | User Story | Outbound load building and dock appointment | Supply Chain/Warehousing | Rahul Verma | New | ZAV-HZN\Sprint 5 | 8 |  | scm; WMS | 2026-10-09 13:08
4176 | User Story | Replenishment templates for fast movers | Supply Chain/Warehousing | Rahul Verma | New | ZAV-HZN\Sprint 5 | 5 |  | scm; WMS | 2026-10-10 14:25
4177 | User Story | Mobile app putaway on handheld | Supply Chain/Warehousing | Rahul Verma | New | ZAV-HZN\Sprint 5 | 3 |  | scm; WMS; device-decision | 2026-10-11 15:42
4178 | User Story | Customer portal for shipment tracking (CR-008, pending approval) | Sales & Service CE | Lina Mansour | New | ZAV-HZN\Sprint 5 | 13 |  | ce; CR-008 | 2026-10-12 16:59
4179 | User Story | Knowledge articles for top 10 case categories | Sales & Service CE | Lina Mansour | New | ZAV-HZN\Sprint 5 | 3 |  | ce | 2026-10-13 09:16
4180 | User Story | Quote approval matrix by margin | Sales & Service CE | Lina Mansour | New | ZAV-HZN\Sprint 5 | 5 |  | ce | 2026-10-14 10:33
4181 | User Story | Vendor master de-duplicated trial load 2 | Data Migration | Noura Al Hashimi | New | ZAV-HZN\Sprint 5 | 5 |  | dm; vendor-dedup; trial-load | 2026-10-15 11:50
4182 | User Story | Open AP/AR items extraction from GP 2018 | Data Migration | Noura Al Hashimi | New | ZAV-HZN\Sprint 5 | 5 |  | dm; trial-load | 2026-10-16 12:07
4183 | User Story | Tally (KSA) opening balance mapping | Data Migration | Noura Al Hashimi | New | ZAV-HZN\Sprint 5 | 3 |  | dm; ZVSA | 2026-10-05 13:24
4184 | User Story | CargoWise file-based fallback interface (contingency) | Integration | Arjun Mehta | New | ZAV-HZN\Sprint 5 | 8 |  | int; CargoWise; fallback | 2026-10-06 14:41
4185 | User Story | Integration monitoring dashboard in Azure Monitor | Integration | Arjun Mehta | New | ZAV-HZN\Sprint 5 | 3 |  | int | 2026-10-07 15:58
4186 | Task | Bank payment file format – Oman | Integration | Arjun Mehta | New | ZAV-HZN\Sprint 5 |  | 8 | int | 2026-10-08 16:15
4187 | User Story | Copilot training wave 2 – Customer service agent persona | Change & Copilot Adoption | Tom Becker | New | ZAV-HZN\Sprint 5 | 3 |  | chg; copilot | 2026-10-09 09:32
4188 | User Story | Sensitivity labels for HR-Payroll and Finance-Board sites | Change & Copilot Adoption | Tom Becker | New | ZAV-HZN\Sprint 5 | 2 |  | chg; copilot; oversharing | 2026-10-10 10:49
4189 | Bug | Duplicate contact created on email-to-case | Sales & Service CE | Lina Mansour | New | ZAV-HZN\Sprint 5 | 2 |  | ce | 2026-10-11 11:06
4190 | Task | Sprint 5 planning and capacity check | Finance | Priya Nair | New | ZAV-HZN\Sprint 5 |  | 8 | fin | 2026-10-12 12:23

## Sprint summary
ZAV-HZN sprint summary ¦ Fictitious test data – Copilot for Frontier Consultancy scenario testing
Sprint | Items | Story points (total) | Points – New | Points – Active | Points – Resolved | Points – Closed | Points – Blocked | Points completed | Completion % | Blocked items | Remaining work (h)
ZAV-HZN\Sprint 3 | 22 | 70 | 0 | 0 | 5 | 65 | 0 | 70 | 100% | 0 | 0
ZAV-HZN\Sprint 4 | 28 | 100 | 6 | 6 | 13 | 57 | 18 | 70 | 70% | 6 | 38
ZAV-HZN\Sprint 5 | 20 | 89 | 89 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 16
Total (Sprints 3–5) | 70 | 259 | 95 | 6 | 18 | 122 | 18 | 140 | 54.05% | 6 | 54
Sprint 4 blocked items tagged CargoWise | 6
Sprint 4 end date | 2026-10-23
Check: items on Backlog (all sprints + release) | 90