## Read me
Frontier Consulting – D365 Estimation Model
Fictitious test data – Copilot for Frontier Consultancy scenario testing
Item | Detail
Purpose | Frontier Consulting's practice estimation template for Microsoft Dynamics 365 bids (Business Applications practice, owner Lorette Roos). It converts counts of build items by complexity into effort days, adds phase overheads by role and prices the result at the standard day rates. Used in test scenarios where Copilot estimates the Zava bid (ZAV-RFP-2026-014).
Test-data notice | Fictitious test data – Copilot for Frontier Consultancy scenario testing. All companies, people and figures are fictitious.
How to use | 1) Check day rates on Parameters. 2) Check effort days on Complexity Matrix. 3) Check overhead percentages on Phase Overheads. 4) On Estimate, enter counts of Simple / Medium / Complex items in the blue cells. Effort by role, cost and checks calculate automatically.
Method | Build days = Σ(count × matrix days). Architect design & review = build days × architect % for the item type. Overheads (PM 12%, Testing 20%, Training 6%) are a % of total build & design days, assigned to one role each. Contingency 10% is applied to every role's subtotal. Cost = total days × role day rate.
Colour legend | Blue font = input you may change · Black = formula · Green = value pulled from another sheet · Teal fill = totals
Day rates (AED) | Architect 6,500 · Functional consultant 5,200 · Developer 4,800 · PM 6,000 · Data 4,800 · Change 4,500 (source: Frontier 2026 rate card)
Sheet map
Parameters | Day rates by role (AED).
Complexity Matrix | Effort days per item type × complexity, primary role and architect %.
Phase Overheads | PM, Testing, Training and Contingency percentages and the role each is assigned to.
Estimate | Item counts → build days → overheads by role → total days and cost, with reconciliation checks.
Fictitious test data – Copilot for Frontier Consultancy scenario testing

## Parameters
Parameters – day rates (AED)
Blue = input you may change · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Role | Day rate (AED) | Typical Frontier staff | Notes
Architect | 6500 | Omar Khalil (CE + Power Platform), James Okafor (F&O / Finance) | Standard 2026 practice rate, excl. VAT
Functional consultant | 5200 | Lina Mansour, Rahul Verma | Standard 2026 practice rate, excl. VAT
Developer | 4800 | Arjun Mehta | Standard 2026 practice rate, excl. VAT
PM | 6000 | Priya Nair | Standard 2026 practice rate, excl. VAT
Data | 4800 | Noura Al Hashimi | Standard 2026 practice rate, excl. VAT
Change | 4500 | Tom Becker | Standard 2026 practice rate, excl. VAT
Currency | AED
Working days per week | 5
Rate card effective | 2026-01-01

## Complexity Matrix
Complexity matrix – effort days per item
Days of build effort per item, by complexity · Blue = input · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Item type | Simple (days) | Medium (days) | Complex (days) | Primary role | Architect design & review (% of build) | Definition / examples
Configuration | 0.5 | 1.5 | 4 | Functional consultant | 5% | Entity/table, field, business rule, security role or parameter set-up
Extension | 2 | 5 | 12 | Developer | 15% | Custom code or ISV extension to standard process
Integration | 5 | 12 | 25 | Developer | 20% | Interface to an external system (API, file, dual-write customisation)
Report | 1.5 | 4 | 8 | Developer | 5% | Power BI report, SSRS / Word template, financial report
Data migration object | 3 | 6 | 12 | Data | 10% | One entity migrated end-to-end: extract, map, cleanse, load, reconcile
Form/view | 0.5 | 1 | 2.5 | Functional consultant | 0% | Main form, quick-create form, view or dashboard
Workflow/Power Automate | 1 | 2.5 | 6 | Functional consultant | 5% | Approval workflow, Power Automate cloud flow, BPF
Plug-in | 1.5 | 4 | 8 | Developer | 10% | C# Dataverse plug-in or custom API
X++ class | 2 | 5 | 10 | Developer | 15% | X++ class, chain-of-command extension or batch job in F&O

## Phase Overheads
Phase overheads – applied to total build & design days
Blue = input · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Overhead | % of build effort | Assigned role | Basis
Project management | 12% | PM | % of total build & design days (Estimate!H18)
Testing | 20% | Functional consultant | % of total build & design days – SIT, UAT support, regression
Training | 6% | Change | % of total build & design days – train-the-trainer, materials
Contingency | 10% | All roles (pro rata) | % of each role's subtotal (build + overheads)
Total overhead before contingency | 38%

## Estimate
Estimate – effort and cost by role
Enter item counts in blue cells; everything else is calculated · Fictitious test data – Copilot for Frontier Consultancy scenario testing
Customer | Zava LLC
Opportunity / bid ref | ZAV-RFP-2026-014
Estimate status | Worked example with illustrative counts – replace counts with the RFP-driven item list
Item type | Simple (count) | Medium (count) | Complex (count) | Build days | Primary role | Architect days | Total build & design days
Configuration | 40 | 25 | 8 | 89.5 | Functional consultant | 4.475 | 93.975
Extension | 3 | 5 | 2 | 55 | Developer | 8.25 | 63.25
Integration | 1 | 3 | 2 | 91 | Developer | 18.2 | 109.2
Report | 6 | 5 | 2 | 45 | Developer | 2.25 | 47.25
Data migration object | 6 | 8 | 4 | 114 | Data | 11.4 | 125.4
Form/view | 20 | 12 | 4 | 32 | Functional consultant | 0 | 32
Workflow/Power Automate | 8 | 6 | 2 | 35 | Functional consultant | 1.75 | 36.75
Plug-in | 3 | 4 | 2 | 36.5 | Developer | 3.65 | 40.15
X++ class | 2 | 3 | 1 | 29 | Developer | 4.35 | 33.35
Total | 89 | 71 | 27 | 527 |  | 54.325 | 581.325
Role | Build & design days | Project management | Testing | Training | Subtotal days | Contingency | Total days | Day rate (AED) | Cost (AED)
Architect | 54.325 | 0 | 0 | 0 | 54.325 | 5.4325 | 59.7575 | 6500 | 388423.75
Functional consultant | 156.5 | 0 | 116.265 | 0 | 272.765 | 27.2765 | 300.0415 | 5200 | 1560215.8
Developer | 256.5 | 0 | 0 | 0 | 256.5 | 25.65 | 282.15 | 4800 | 1354320
PM | 0 | 69.759 | 0 | 0 | 69.759 | 6.9759 | 76.7349 | 6000 | 460409.4
Data | 114 | 0 | 0 | 0 | 114 | 11.4 | 125.4 | 4800 | 601920
Change | 0 | 0 | 0 | 34.8795 | 34.8795 | 3.488 | 38.3674 | 4500 | 172653.525
Total | 581.325 | 69.759 | 116.265 | 34.8795 | 802.2285 | 80.2228 | 882.4513 | 5142.4279 | 4537942.475
← blended rate
Key results
Total effort (days) | 882.4513
Total fees (AED) | 4537942.475
Blended day rate (AED) | 5142.4279
Overheads as % of build | 38%
Check: overheads reconcile (should be 0) | 0
Check: build days reconcile (should be 0) | 0